## Jira Import
Issue ID | Parent ID | Issue Type | Summary | Description | Epic Name | Epic Link | Priority | Story Points | Original Estimate (h) | Component | Milestone | Labels
EPIC-A |  | Epic | A — Foundation & tenancy | Auth, workspaces, spaces, folders and the application-layer scoping that isolates every tenant. | Foundation & tenancy |  |  | 31 | 145 |  |  | epic
A1 | EPIC-A | Story | As a new user, I can sign up and create a workspace so I have somewhere to put documents. | Email plus magic-link auth. Creating a workspace makes the creator its admin. |  | EPIC-A | Highest | 5 | 28 |  | M0 Foundation | p0,m0
A1-T1 | A1 | Sub-task | Sanctum SPA session auth plus signed-URL magic links |  |  |  | Highest |  | 10 | Backend | M0 Foundation | backend
A1-T2 | A1 | Sub-task | Build sign in / sign up screen (S1) |  |  |  | Highest |  | 8 | Frontend | M0 Foundation | frontend
A1-T3 | A1 | Sub-task | Workspace creation flow with slug validation (S2) |  |  |  | Highest |  | 6 | Full stack | M0 Foundation | full-stack
A1-T4 | A1 | Sub-task | Users table and workspace membership model |  |  |  | Highest |  | 4 | Database | M0 Foundation | database
A2 | EPIC-A | Story | As an admin, I can invite teammates by email with a role so they can join the workspace. | Invite by email with a role assigned at invite time. |  | EPIC-A | Highest | 5 | 20 |  | M0 Foundation | p0,m0
A2-T1 | A2 | Sub-task | Invite API with signed token and email delivery |  |  |  | Highest |  | 8 | Backend | M0 Foundation | backend
A2-T2 | A2 | Sub-task | Invite and accept screens (S3) |  |  |  | Highest |  | 8 | Frontend | M0 Foundation | frontend
A2-T3 | A2 | Sub-task | Role assignment on invite acceptance |  |  |  | Highest |  | 4 | Backend | M0 Foundation | backend
A3 | EPIC-A | Story | As a developer, every tenant table is workspace-scoped by default so no query can cross a workspace boundary. | Release blocker. MySQL has no row-level security, so the boundary is application-layer: a missed scope leaks rather than returning nothing. |  | EPIC-A | Highest | 13 | 60 |  | M0 Foundation | p0,m0
A3-T1 | A3 | Sub-task | Build TenantModel base class with mandatory workspace global scope |  |  |  | Highest |  | 10 | Backend | M0 Foundation | backend
A3-T2 | A3 | Sub-task | Auto-set workspace_id on create from request context, never from payload |  |  |  | Highest |  | 5 | Backend | M0 Foundation | backend
A3-T3 | A3 | Sub-task | Laravel Policies for space-level access |  |  |  | Highest |  | 10 | Backend | M0 Foundation | backend
A3-T4 | A3 | Sub-task | Schema conformance test: every tenant table scoped, indexed, non-fillable |  |  |  | Highest |  | 12 | QA | M0 Foundation | qa
A3-T5 | A3 | Sub-task | Static analysis rule blocking raw unscoped queries |  |  |  | Highest |  | 6 | Infra | M0 Foundation | infra
A3-T6 | A3 | Sub-task | Cross-tenant and cross-table consistency test suite |  |  |  | Highest |  | 14 | QA | M0 Foundation | qa
A3-T7 | A3 | Sub-task | Wire all gates into CI as blocking |  |  |  | Highest |  | 3 | Infra | M0 Foundation | infra
A4 | EPIC-A | Story | As an admin, I can create spaces and folders so documentation matches how the company is organised. | Workspace to space to folder, max depth 5. |  | EPIC-A | Highest | 5 | 23 |  | M0 Foundation | p0,m0
A4-T1 | A4 | Sub-task | Schema and migrations for spaces and folders |  |  |  | Highest |  | 5 | Database | M0 Foundation | database
A4-T2 | A4 | Sub-task | Folder CRUD API including move with depth check |  |  |  | Highest |  | 8 | Backend | M0 Foundation | backend
A4-T3 | A4 | Sub-task | Sidebar tree and space browser (S5, S6) |  |  |  | Highest |  | 10 | Frontend | M0 Foundation | frontend
A5 | EPIC-A | Story | As a user, I see only the spaces I'm a member of, everywhere in the product. | No greyed-out items hinting at content behind a permission wall. |  | EPIC-A | Highest | 3 | 14 |  | M0 Foundation | p0,m0
A5-T1 | A5 | Sub-task | Scope sidebar and browser to accessible spaces |  |  |  | Highest |  | 5 | Frontend | M0 Foundation | frontend
A5-T2 | A5 | Sub-task | Return 403 not 404 so existence is never leaked |  |  |  | Highest |  | 5 | Backend | M0 Foundation | backend
A5-T3 | A5 | Sub-task | Permission visibility tests across surfaces |  |  |  | Highest |  | 4 | QA | M0 Foundation | qa
EPIC-B |  | Epic | B — Editor & document model | The block editor, the structured SOP model, templates and paste fidelity. | Editor & document model |  |  | 40 | 163 |  |  | epic
B1 | EPIC-B | Story | As an editor, I can write a document with headings, lists, tables, callouts and images. | Content stored as structured JSON, never HTML, so diffing and chunking stay reliable. |  | EPIC-B | Highest | 13 | 64 |  | M0 Foundation | p0,m0
B1-T1 | B1 | Sub-task | Editor foundation and structured JSON document model |  |  |  | Highest |  | 20 | Frontend | M0 Foundation | frontend
B1-T2 | B1 | Sub-task | Core blocks: headings, lists, tables, callouts, code |  |  |  | Highest |  | 20 | Frontend | M0 Foundation | frontend
B1-T3 | B1 | Sub-task | Image upload to object storage, referenced by ID |  |  |  | Highest |  | 10 | Full stack | M0 Foundation | full-stack
B1-T4 | B1 | Sub-task | Reader render parity with editor |  |  |  | Highest |  | 8 | Frontend | M0 Foundation | frontend
B1-T5 | B1 | Sub-task | Round-trip save/load fidelity tests |  |  |  | Highest |  | 6 | QA | M0 Foundation | qa
B2 | EPIC-B | Story | As an editor, my work autosaves so I never lose a draft. | Debounced at 2s with an explicit saved indicator, never a spinner. |  | EPIC-B | Highest | 3 | 14 |  | M0 Foundation | p0,m0
B2-T1 | B2 | Sub-task | Debounced autosave and saved-state indicator |  |  |  | Highest |  | 6 | Frontend | M0 Foundation | frontend
B2-T2 | B2 | Sub-task | Optimistic concurrency via expected_updated_at and 409 |  |  |  | Highest |  | 6 | Backend | M0 Foundation | backend
B2-T3 | B2 | Sub-task | Mid-edit tab close recovery test |  |  |  | Highest |  | 2 | QA | M0 Foundation | qa
B3 | EPIC-B | Story | As an editor, I can build an SOP with structured steps I can reorder and renumber automatically. | Steps are rows as well as content, so they can be cited by ID. |  | EPIC-B | Highest | 8 | 28 |  | M0 Foundation | p0,m0
B3-T1 | B3 | Sub-task | document_steps schema and step CRUD API |  |  |  | Highest |  | 8 | Backend | M0 Foundation | backend
B3-T2 | B3 | Sub-task | Step editor with drag reorder and live renumber (S8) |  |  |  | Highest |  | 14 | Frontend | M0 Foundation | frontend
B3-T3 | B3 | Sub-task | Block submit when a SOP has zero steps |  |  |  | Highest |  | 3 | Backend | M0 Foundation | backend
B3-T4 | B3 | Sub-task | Reorder and renumber correctness tests |  |  |  | Highest |  | 3 | QA | M0 Foundation | qa
B4 | EPIC-B | Story | As an editor, I can mark a step critical or a checkpoint so readers see what matters. | Critical steps always appear in chatbot answers about that process. |  | EPIC-B | High | 3 | 10 |  | M0 Foundation | p1,m0
B4-T1 | B4 | Sub-task | Add critical and checkpoint flags to schema and API |  |  |  | High |  | 3 | Backend | M0 Foundation | backend
B4-T2 | B4 | Sub-task | Editor controls and reader amber-rule treatment |  |  |  | High |  | 7 | Frontend | M0 Foundation | frontend
B5 | EPIC-B | Story | As an editor, I can start from a template (blank, onboarding, playbook, policy). | Workspaces can also save their own templates. |  | EPIC-B | High | 5 | 19 |  | M0 Foundation | p1,m0
B5-T1 | B5 | Sub-task | Template storage and four seeded templates |  |  |  | High |  | 6 | Backend | M0 Foundation | backend
B5-T2 | B5 | Sub-task | Template picker and create-from-template flow |  |  |  | High |  | 8 | Frontend | M0 Foundation | frontend
B5-T3 | B5 | Sub-task | Workspace-defined custom templates |  |  |  | High |  | 5 | Full stack | M0 Foundation | full-stack
B6 | EPIC-B | Story | As an editor, I can paste from Google Docs or Notion without losing structure. | Headings, lists and tables must survive, including nesting. |  | EPIC-B | High | 5 | 17 |  | M0 Foundation | p1,m0
B6-T1 | B6 | Sub-task | Paste transformer for headings, lists and tables |  |  |  | High |  | 12 | Frontend | M0 Foundation | frontend
B6-T2 | B6 | Sub-task | Nested list and table fidelity tests across sources |  |  |  | High |  | 5 | QA | M0 Foundation | qa
B7 | EPIC-B | Story | As an editor, I can link to another internal document. | Cross-linking replaces multi-filing; a document lives in one folder. |  | EPIC-B | High | 3 | 11 |  | M0 Foundation | p1,m0
B7-T1 | B7 | Sub-task | Internal link block and document picker |  |  |  | High |  | 7 | Frontend | M0 Foundation | frontend
B7-T2 | B7 | Sub-task | Backlink resolution and broken-link handling |  |  |  | High |  | 4 | Backend | M0 Foundation | backend
EPIC-C |  | Epic | C — Recording capture | Browser screen capture, resumable upload and honest pipeline status. | Recording capture |  |  | 29 | 100 |  |  | epic
C1 | EPIC-C | Story | As a contributor, I can record my screen and voice in the browser and upload it. | Browser capture only for v1. Half of the wedge. |  | EPIC-C | Highest | 13 | 43 |  | M1 Prove the wedge | p0,m1
C1-T1 | C1 | Sub-task | Screen and mic capture via getDisplayMedia and MediaRecorder |  |  |  | Highest |  | 14 | Frontend | M1 Prove the wedge | frontend
C1-T2 | C1 | Sub-task | Permission primer before the browser prompt (S11) |  |  |  | Highest |  | 5 | Design | M1 Prove the wedge | design
C1-T3 | C1 | Sub-task | Presigned S3 multipart upload direct to Spaces via Flysystem |  |  |  | Highest |  | 10 | Backend | M1 Prove the wedge | backend
C1-T4 | C1 | Sub-task | recordings schema and upload registration endpoint |  |  |  | Highest |  | 6 | Backend | M1 Prove the wedge | backend
C1-T5 | C1 | Sub-task | Cross-browser capture verification (Chrome, Edge, Firefox, Safari) |  |  |  | Highest |  | 8 | QA | M1 Prove the wedge | qa
C2 | EPIC-C | Story | As a contributor, I can drag and drop an existing recording file. | Accepts webm, mp4, mov up to 60 minutes and 2 GB. |  | EPIC-C | Highest | 3 | 9 |  | M1 Prove the wedge | p0,m1
C2-T1 | C2 | Sub-task | Drop zone with format and size validation |  |  |  | Highest |  | 6 | Frontend | M1 Prove the wedge | frontend
C2-T2 | C2 | Sub-task | Server-side format and limit validation |  |  |  | Highest |  | 3 | Backend | M1 Prove the wedge | backend
C3 | EPIC-C | Story | As a contributor, my upload resumes after a network interruption. | A 45-minute upload must survive one dropped connection. |  | EPIC-C | Highest | 8 | 28 |  | M1 Prove the wedge | p0,m1
C3-T1 | C3 | Sub-task | Chunked upload with retry and resume |  |  |  | Highest |  | 14 | Frontend | M1 Prove the wedge | frontend
C3-T2 | C3 | Sub-task | Multipart completion and integrity check |  |  |  | Highest |  | 8 | Backend | M1 Prove the wedge | backend
C3-T3 | C3 | Sub-task | Interrupted-network upload test |  |  |  | Highest |  | 6 | QA | M1 Prove the wedge | qa
C4 | EPIC-C | Story | As a contributor, I can see the processing status of my recording at every stage. | Determinate progress, and failures that say what to do next. |  | EPIC-C | Highest | 5 | 20 |  | M1 Prove the wedge | p0,m1
C4-T1 | C4 | Sub-task | pipeline_jobs table and status transitions |  |  |  | Highest |  | 6 | Backend | M1 Prove the wedge | backend
C4-T2 | C4 | Sub-task | Status polling and recordings list (S10); Reverb deferred to M3 |  |  |  | Highest |  | 10 | Frontend | M1 Prove the wedge | frontend
C4-T3 | C4 | Sub-task | Plain-language failure reasons with retry |  |  |  | Highest |  | 4 | Full stack | M1 Prove the wedge | full-stack
EPIC-D |  | Epic | D — AI SOP generation | The wedge. Recording in, structured draft procedure out. | AI SOP generation |  |  | 52 | 195 |  |  | epic
D0 | EPIC-D | Story | As a team, we've chosen a transcription provider on evidence from real recordings. | The Claude API has no speech-to-text endpoint, so the stack does not yet include one. Blocks the wedge. |  | EPIC-D | Highest | 5 | 18 |  | M1 Prove the wedge | p0,m1
D0-T1 | D0 | Sub-task | Assemble 10-recording evaluation set spanning length, accent and noise |  |  |  | Highest |  | 5 | QA | M1 Prove the wedge | qa
D0-T2 | D0 | Sub-task | Benchmark Whisper API and Deepgram on timestamp accuracy and cost |  |  |  | Highest |  | 10 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D0-T3 | D0 | Sub-task | Confirm zero-retention terms with the chosen provider |  |  |  | Highest |  | 3 | Backend | M1 Prove the wedge | backend
D1 | EPIC-D | Story | As a system, I transcribe an uploaded recording with word-level timestamps. | Halts with a clear message on very low confidence rather than inventing content. |  | EPIC-D | Highest | 8 | 26 |  | M1 Prove the wedge | p0,m1
D1-T1 | D1 | Sub-task | Speech-to-text adapter interface and provider implementation |  |  |  | Highest |  | 10 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D1-T2 | D1 | Sub-task | transcripts schema with word-level timestamps |  |  |  | Highest |  | 5 | Database | M1 Prove the wedge | database
D1-T3 | D1 | Sub-task | Retry policy and low-confidence halt |  |  |  | Highest |  | 6 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D1-T4 | D1 | Sub-task | Job idempotency via job_key |  |  |  | Highest |  | 5 | Backend | M1 Prove the wedge | backend
D2 | EPIC-D | Story | As a system, I segment the transcript into distinct actions. | Falls back to paragraph segmentation if action detection fails. |  | EPIC-D | Highest | 13 | 48 |  | M1 Prove the wedge | p0,m1
D2-T1 | D2 | Sub-task | Transcript cue and pause-based segmentation |  |  |  | Highest |  | 16 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D2-T2 | D2 | Sub-task | Visual scene-change detection |  |  |  | Highest |  | 14 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D2-T3 | D2 | Sub-task | Segment merge logic and paragraph fallback |  |  |  | Highest |  | 8 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D2-T4 | D2 | Sub-task | Segmentation accuracy eval on 20 real recordings |  |  |  | Highest |  | 10 | QA | M1 Prove the wedge | qa
D3 | EPIC-D | Story | As a system, I extract one deduplicated key frame per detected action. | Continues without screenshots rather than failing the whole generation. |  | EPIC-D | Highest | 8 | 24 |  | M1 Prove the wedge | p0,m1
D3-T1 | D3 | Sub-task | Frame extraction per segment via ffmpeg |  |  |  | Highest |  | 10 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D3-T2 | D3 | Sub-task | Perceptual dedup of near-identical frames |  |  |  | Highest |  | 8 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D3-T3 | D3 | Sub-task | Store frames as media_assets with step linkage |  |  |  | Highest |  | 6 | Backend | M1 Prove the wedge | backend
D4 | EPIC-D | Story | As a contributor, a structured draft SOP is generated with purpose, scope, numbered steps, screenshots and outcome. | Always a draft. Never auto-approved, never auto-indexed. |  | EPIC-D | Highest | 13 | 52 |  | M1 Prove the wedge | p0,m1
D4-T1 | D4 | Sub-task | Generation prompt and structured output schema |  |  |  | Highest |  | 16 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D4-T2 | D4 | Sub-task | Per-segment transcript summarisation for cost control |  |  |  | Highest |  | 8 | AI/Pipeline | M1 Prove the wedge | ai-pipeline
D4-T3 | D4 | Sub-task | Draft document and step assembly from model output |  |  |  | Highest |  | 10 | Backend | M1 Prove the wedge | backend
D4-T4 | D4 | Sub-task | Re-run creates a new draft and never overwrites edits |  |  |  | Highest |  | 6 | Backend | M1 Prove the wedge | backend
D4-T5 | D4 | Sub-task | Generation eval set and scoring harness (20 recordings) |  |  |  | Highest |  | 12 | QA | M1 Prove the wedge | qa
D5 | EPIC-D | Story | As a contributor, each generated step links back to its timestamp in the recording so I can verify it. | Submit stays disabled until every step is verified or edited. |  | EPIC-D | Highest | 5 | 27 |  | M1 Prove the wedge | p0,m1
D5-T1 | D5 | Sub-task | Persist source timestamps on generated steps |  |  |  | Highest |  | 3 | Backend | M1 Prove the wedge | backend
D5-T2 | D5 | Sub-task | Draft review screen with bound scrubber and steps (S9) |  |  |  | Highest |  | 16 | Frontend | M1 Prove the wedge | frontend
D5-T3 | D5 | Sub-task | Verify control and submit gating |  |  |  | Highest |  | 8 | Frontend | M1 Prove the wedge | frontend
EPIC-E |  | Epic | E — Governance | Approval workflow, versioning, diffs and the audit trail. | Governance |  |  | 34 | 123 |  |  | epic
E1 | EPIC-E | Story | As an owner, I can submit a draft for review and approve or request changes. | Self-approval is off by default. Request changes needs a comment. |  | EPIC-E | High | 8 | 30 |  | M2 Design partners | p1,m2
E1-T1 | E1 | Sub-task | Approval state machine and transition guards |  |  |  | High |  | 8 | Backend | M2 Design partners | backend
E1-T2 | E1 | Sub-task | Self-approval workspace setting enforcement |  |  |  | High |  | 3 | Backend | M2 Design partners | backend
E1-T3 | E1 | Sub-task | Approval review screen, diff as default view (S12) |  |  |  | High |  | 12 | Frontend | M2 Design partners | frontend
E1-T4 | E1 | Sub-task | In-app and email review notifications |  |  |  | High |  | 7 | Full stack | M2 Design partners | full-stack
E2 | EPIC-E | Story | As a reader, I see an approved-by and version badge so I know I can trust it. | The control block above the title. |  | EPIC-E | High | 3 | 9 |  | M2 Design partners | p1,m2
E2-T1 | E2 | Sub-task | Control block in document reader (S7) |  |  |  | High |  | 6 | Frontend | M2 Design partners | frontend
E2-T2 | E2 | Sub-task | Expose version and approver metadata via API |  |  |  | High |  | 3 | Backend | M2 Design partners | backend
E3 | EPIC-E | Story | As an owner, editing an approved document creates a new draft while the approved version stays live. | The most misunderstood behaviour in the product. Needs an on-screen banner. |  | EPIC-E | High | 8 | 27 |  | M2 Design partners | p1,m2
E3-T1 | E3 | Sub-task | Trigger: edit after approval flips state to draft |  |  |  | High |  | 6 | Database | M2 Design partners | database
E3-T2 | E3 | Sub-task | Split working copy from approved version in API |  |  |  | High |  | 10 | Backend | M2 Design partners | backend
E3-T3 | E3 | Sub-task | Editor banner explaining the live version (S8) |  |  |  | High |  | 5 | Frontend | M2 Design partners | frontend
E3-T4 | E3 | Sub-task | Draft-vs-live behaviour tests |  |  |  | High |  | 6 | QA | M2 Design partners | qa
E4 | EPIC-E | Story | As an owner, I can see the full version history and a block-level diff between any two versions. | Moved blocks marked as moved, not as a delete plus an add. |  | EPIC-E | High | 8 | 34 |  | M2 Design partners | p1,m2
E4-T1 | E4 | Sub-task | document_versions schema and numbering trigger |  |  |  | High |  | 6 | Database | M2 Design partners | database
E4-T2 | E4 | Sub-task | Block-level diff algorithm including move detection |  |  |  | High |  | 16 | Backend | M2 Design partners | backend
E4-T3 | E4 | Sub-task | Version history and diff screen (S13) |  |  |  | High |  | 12 | Frontend | M2 Design partners | frontend
E5 | EPIC-E | Story | As an owner, I can restore an old version as a new draft. | Restore never overwrites the live approved version. |  | EPIC-E | High | 3 | 7 |  | M2 Design partners | p1,m2
E5-T1 | E5 | Sub-task | Restore endpoint creating a draft |  |  |  | High |  | 4 | Backend | M2 Design partners | backend
E5-T2 | E5 | Sub-task | Restore confirmation stating the consequence |  |  |  | High |  | 3 | Frontend | M2 Design partners | frontend
E6 | EPIC-E | Story | As an admin, every state change is written to an append-only audit log. | Insert and select grants only. No update, no delete. |  | EPIC-E | High | 4 | 16 |  | M2 Design partners | p1,m2
E6-T1 | E6 | Sub-task | audit_log table with append-only grants |  |  |  | High |  | 4 | Database | M2 Design partners | database
E6-T2 | E6 | Sub-task | Audit write triggers for state and permission changes |  |  |  | High |  | 6 | Backend | M2 Design partners | backend
E6-T3 | E6 | Sub-task | Audit log screen with export (S21) |  |  |  | High |  | 6 | Frontend | M2 Design partners | frontend
EPIC-F |  | Epic | F — Permissions | Roles, folder overrides and immediate revocation. | Permissions |  |  | 21 | 70 |  |  | epic
F1 | EPIC-F | Story | As an admin, I can assign admin, approver, editor, reader and guest roles per space. | Space is the primary permission boundary. |  | EPIC-F | High | 8 | 26 |  | M2 Design partners | p1,m2
F1-T1 | F1 | Sub-task | space_members schema and role enum |  |  |  | High |  | 4 | Database | M2 Design partners | database
F1-T2 | F1 | Sub-task | Role assignment API with transition guards |  |  |  | High |  | 8 | Backend | M2 Design partners | backend
F1-T3 | F1 | Sub-task | Members and roles screen (S18) |  |  |  | High |  | 10 | Frontend | M2 Design partners | frontend
F1-T4 | F1 | Sub-task | Consequence-stating confirmation copy |  |  |  | High |  | 4 | Design | M2 Design partners | design
F2 | EPIC-F | Story | As an admin, I can override permissions at folder level and inspect the effective result per user. | Permission bugs are comprehension failures; the inspector is the fix. |  | EPIC-F | High | 8 | 30 |  | M2 Design partners | p1,m2
F2-T1 | F2 | Sub-task | Folder override model and resolution logic |  |  |  | High |  | 12 | Backend | M2 Design partners | backend
F2-T2 | F2 | Sub-task | Effective permission inspector (S19) |  |  |  | High |  | 12 | Frontend | M2 Design partners | frontend
F2-T3 | F2 | Sub-task | Resolution correctness test matrix |  |  |  | High |  | 6 | QA | M2 Design partners | qa
F3 | EPIC-F | Story | As an admin, removing someone's access immediately removes those documents from their search and chat. | No cache window in which a removed user still gets answers. |  | EPIC-F | High | 5 | 14 |  | M2 Design partners | p1,m2
F3-T1 | F3 | Sub-task | Synchronous retrieval-scope update on membership change |  |  |  | High |  | 8 | Backend | M2 Design partners | backend
F3-T2 | F3 | Sub-task | No-cache-window revocation verification test |  |  |  | High |  | 6 | QA | M2 Design partners | qa
EPIC-G |  | Epic | G — Search & retrieval | Provider selection, chunking, embedding, hybrid ranking and in-query permission filtering. | Search & retrieval |  |  | 47 | 155 |  |  | epic
G0 | EPIC-G | Story | As a team, we've chosen an embeddings provider and a vector store, and proven them on real content. | Claude has no embeddings endpoint and MySQL 8.4 has no VECTOR type. Both are open decisions. |  | EPIC-G | High | 5 | 21 |  | M3 Retrieval layer | p1,m3
G0-T1 | G0 | Sub-task | Benchmark Voyage AI and OpenAI embeddings on the retrieval eval set |  |  |  | High |  | 10 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
G0-T2 | G0 | Sub-task | Stand up Qdrant on DigitalOcean and compare against managed Pinecone |  |  |  | High |  | 8 | Infra | M3 Retrieval layer | infra
G0-T3 | G0 | Sub-task | Record embed_model per chunk so a provider change is a targetable re-embed |  |  |  | High |  | 3 | Backend | M3 Retrieval layer | backend
G1 | EPIC-G | Story | As a system, I chunk approved documents by step and section and embed them on approval. | Chunking on semantic boundaries, not fixed token windows. Runs on approval only. |  | EPIC-G | High | 13 | 43 |  | M3 Retrieval layer | p1,m3
G1-T1 | G1 | Sub-task | Semantic chunking by step and section |  |  |  | High |  | 12 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
G1-T2 | G1 | Sub-task | document_chunks schema with section_ref |  |  |  | High |  | 5 | Database | M3 Retrieval layer | database
G1-T3 | G1 | Sub-task | Embedding job and vector upsert on approval |  |  |  | High |  | 10 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
G1-T4 | G1 | Sub-task | Vector store adapter (Pinecone or Qdrant) |  |  |  | High |  | 10 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
G1-T5 | G1 | Sub-task | Unindexed-approved-document monitor and alert |  |  |  | High |  | 6 | Infra | M3 Retrieval layer | infra
G2 | EPIC-G | Story | As a user, I can search by meaning and find documents phrased differently from my query. | p95 under 800ms on a 5,000-document workspace. |  | EPIC-G | High | 8 | 24 |  | M3 Retrieval layer | p1,m3
G2-T1 | G2 | Sub-task | Query embedding and vector search path |  |  |  | High |  | 8 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
G2-T2 | G2 | Sub-task | Search results screen (S14) |  |  |  | High |  | 10 | Frontend | M3 Retrieval layer | frontend
G2-T3 | G2 | Sub-task | Relevance eval set of 50 query/document pairs |  |  |  | High |  | 6 | QA | M3 Retrieval layer | qa
G3 | EPIC-G | Story | As a user, results are hybrid-ranked across semantic and keyword matching. | Reciprocal rank fusion over vector and full-text results. |  | EPIC-G | High | 8 | 28 |  | M3 Retrieval layer | p1,m3
G3-T1 | G3 | Sub-task | MySQL FULLTEXT index, custom stopwords, min token size config |  |  |  | High |  | 10 | Backend | M3 Retrieval layer | backend
G3-T2 | G3 | Sub-task | Reciprocal rank fusion by position, not raw score, with weight tuning |  |  |  | High |  | 12 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
G3-T3 | G3 | Sub-task | Ranking quality eval |  |  |  | High |  | 6 | QA | M3 Retrieval layer | qa
G4 | EPIC-G | Story | As a user, I can filter results by space, owner, type and date. |  |  | EPIC-G | High | 5 | 13 |  | M3 Retrieval layer | p1,m3
G4-T1 | G4 | Sub-task | Filter parameters on search API |  |  |  | High |  | 5 | Backend | M3 Retrieval layer | backend
G4-T2 | G4 | Sub-task | Filter rail UI |  |  |  | High |  | 8 | Frontend | M3 Retrieval layer | frontend
G5 | EPIC-G | Story | As a system, retrieval filters by permission inside the query, never after. | Release blocker. Two independent checks must both fail for a leak to occur. |  | EPIC-G | High | 8 | 26 |  | M3 Retrieval layer | p1,m3
G5-T1 | G5 | Sub-task | Workspace, space and state metadata filters on vector query |  |  |  | High |  | 8 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
G5-T2 | G5 | Sub-task | Policy-backed chunk scoping in the query layer |  |  |  | High |  | 6 | Backend | M3 Retrieval layer | backend
G5-T3 | G5 | Sub-task | Adversarial retrieval leak tests including existence probing |  |  |  | High |  | 12 | QA | M3 Retrieval layer | qa
EPIC-H |  | Epic | H — Chatbot | Answers from approved content only, cited, with designed refusal. | Chatbot |  |  | 42 | 124 |  |  | epic
H1 | EPIC-H | Story | As an employee, I can ask a question in plain language and get an answer from our own documents. | p95 first token under 2 seconds. |  | EPIC-H | High | 13 | 44 |  | M3 Retrieval layer | p1,m3
H1-T1 | H1 | Sub-task | Retrieval to context assembly |  |  |  | High |  | 10 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
H1-T2 | H1 | Sub-task | Answer generation prompt requiring citations |  |  |  | High |  | 12 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
H1-T3 | H1 | Sub-task | SSE streaming endpoint |  |  |  | High |  | 8 | Backend | M3 Retrieval layer | backend
H1-T4 | H1 | Sub-task | Ask screen with streaming render (S15) |  |  |  | High |  | 14 | Frontend | M3 Retrieval layer | frontend
H2 | EPIC-H | Story | As an employee, every answer cites the source SOP, version and step, and links to it. | An answer with zero citations is a bug, not a valid response. |  | EPIC-H | High | 8 | 22 |  | M3 Retrieval layer | p1,m3
H2-T1 | H2 | Sub-task | Citation resolution to document, version and step |  |  |  | High |  | 8 | Backend | M3 Retrieval layer | backend
H2-T2 | H2 | Sub-task | Citation chips with deep link to step |  |  |  | High |  | 10 | Frontend | M3 Retrieval layer | frontend
H2-T3 | H2 | Sub-task | Block answers that carry no citation |  |  |  | High |  | 4 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
H3 | EPIC-H | Story | As an employee, when no approved document covers my question, the bot says so instead of guessing. | Refusal is a designed state with actions attached, not a fallback. |  | EPIC-H | High | 8 | 24 |  | M3 Retrieval layer | p1,m3
H3-T1 | H3 | Sub-task | Confidence threshold and refusal path |  |  |  | High |  | 8 | AI/Pipeline | M3 Retrieval layer | ai-pipeline
H3-T2 | H3 | Sub-task | Refusal UI with record and request actions |  |  |  | High |  | 8 | Design | M3 Retrieval layer | design
H3-T3 | H3 | Sub-task | Refusal eval: 15 deliberately unanswerable questions |  |  |  | High |  | 8 | QA | M3 Retrieval layer | qa
H4 | EPIC-H | Story | As an employee, I can ask follow-up questions in the same conversation. |  |  | EPIC-H | High | 5 | 12 |  | M3 Retrieval layer | p1,m3
H4-T1 | H4 | Sub-task | Session history and context window management |  |  |  | High |  | 8 | Backend | M3 Retrieval layer | backend
H4-T2 | H4 | Sub-task | Multi-turn context retention tests |  |  |  | High |  | 4 | QA | M3 Retrieval layer | qa
H5 | EPIC-H | Story | As an employee, I can rate an answer helpful or not. |  |  | EPIC-H | High | 3 | 6 |  | M3 Retrieval layer | p1,m3
H5-T1 | H5 | Sub-task | Rating endpoint and storage on chat_messages |  |  |  | High |  | 3 | Backend | M3 Retrieval layer | backend
H5-T2 | H5 | Sub-task | Rating control in answer UI |  |  |  | High |  | 3 | Frontend | M3 Retrieval layer | frontend
H6 | EPIC-H | Story | As an admin, I can see which questions were refused, so I know which SOP to record next. | Turns the chatbot's failures into the customer's content roadmap. |  | EPIC-H | High | 5 | 16 |  | M3 Retrieval layer | p1,m3
H6-T1 | H6 | Sub-task | Refused query aggregation and ranking |  |  |  | High |  | 6 | Backend | M3 Retrieval layer | backend
H6-T2 | H6 | Sub-task | Knowledge gaps screen with Record-this action (S20) |  |  |  | High |  | 10 | Frontend | M3 Retrieval layer | frontend
EPIC-I |  | Epic | I — AI utilities | Rewrite, translation and instant answers. | AI utilities |  |  | 26 | 67 |  |  | epic
I1 | EPIC-I | Story | As an editor, I can have AI rewrite rough notes into clear procedure language, shown as a proposal I accept or reject. | Never applied silently. The server never mutates a document from an AI call. |  | EPIC-I | High | 8 | 24 |  | M4 Open paid tiers | p1,m4
I1-T1 | I1 | Sub-task | Rewrite endpoint returning a proposal |  |  |  | High |  | 8 | AI/Pipeline | M4 Open paid tiers | ai-pipeline
I1-T2 | I1 | Sub-task | Side-by-side accept and reject panel |  |  |  | High |  | 12 | Frontend | M4 Open paid tiers | frontend
I1-T3 | I1 | Sub-task | Never-auto-apply guard and regression test |  |  |  | High |  | 4 | QA | M4 Open paid tiers | qa
I2 | EPIC-I | Story | As an editor, I can translate a document with one click into a linked translation. | Creates a linked translation rather than replacing the source. |  | EPIC-I | High | 8 | 21 |  | M4 Open paid tiers | p1,m4
I2-T1 | I2 | Sub-task | Translation endpoint creating a linked document |  |  |  | High |  | 8 | AI/Pipeline | M4 Open paid tiers | ai-pipeline
I2-T2 | I2 | Sub-task | Translation UI and language picker |  |  |  | High |  | 8 | Frontend | M4 Open paid tiers | frontend
I2-T3 | I2 | Sub-task | Bidirectional translation link model |  |  |  | High |  | 5 | Database | M4 Open paid tiers | database
I3 | EPIC-I | Story | As an editor, a translation is flagged stale when its source is re-approved. |  |  | EPIC-I | Medium | 5 | 9 |  | M4 Open paid tiers | p2,m4
I3-T1 | I3 | Sub-task | Stale trigger on source re-approval |  |  |  | Medium |  | 4 | Database | M4 Open paid tiers | database
I3-T2 | I3 | Sub-task | Stale indicator in reader and document list |  |  |  | Medium |  | 5 | Frontend | M4 Open paid tiers | frontend
I4 | EPIC-I | Story | As a user, search shows a direct instant answer above the result list. | Styled as a document extract, not a chat bubble. |  | EPIC-I | Medium | 5 | 13 |  | M4 Open paid tiers | p2,m4
I4-T1 | I4 | Sub-task | Instant answer generation from top result |  |  |  | Medium |  | 6 | AI/Pipeline | M4 Open paid tiers | ai-pipeline
I4-T2 | I4 | Sub-task | Instant answer block in search (S14) |  |  |  | Medium |  | 7 | Frontend | M4 Open paid tiers | frontend
EPIC-J |  | Epic | J — Handbook & acknowledgements | Policy distribution and proof that people read it. | Handbook & acknowledgements |  |  | 21 | 58 |  |  | epic
J1 | EPIC-J | Story | As an HR manager, I can designate a space as the employee handbook with an ordered reader view. |  |  | EPIC-J | High | 5 | 15 |  | M4 Open paid tiers | p1,m4
J1-T1 | J1 | Sub-task | is_handbook flag and ordered view API |  |  |  | High |  | 5 | Backend | M4 Open paid tiers | backend
J1-T2 | J1 | Sub-task | Handbook reader with contents rail (S16) |  |  |  | High |  | 10 | Frontend | M4 Open paid tiers | frontend
J2 | EPIC-J | Story | As an HR manager, I can require acknowledgement of a policy from assigned employees. | Acknowledgement binds to a version, not a document. |  | EPIC-J | High | 8 | 23 |  | M4 Open paid tiers | p1,m4
J2-T1 | J2 | Sub-task | acknowledgements schema, unique per version and user |  |  |  | High |  | 5 | Database | M4 Open paid tiers | database
J2-T2 | J2 | Sub-task | Assign acknowledgement targets API |  |  |  | High |  | 6 | Backend | M4 Open paid tiers | backend
J2-T3 | J2 | Sub-task | Acknowledgement tracking screen, both views (S17) |  |  |  | High |  | 12 | Frontend | M4 Open paid tiers | frontend
J3 | EPIC-J | Story | As an employee, I can acknowledge a policy and it records the version and timestamp. |  |  | EPIC-J | High | 3 | 8 |  | M4 Open paid tiers | p1,m4
J3-T1 | J3 | Sub-task | Acknowledge endpoint |  |  |  | High |  | 3 | Backend | M4 Open paid tiers | backend
J3-T2 | J3 | Sub-task | Sticky acknowledgement bar and confirmation |  |  |  | High |  | 5 | Frontend | M4 Open paid tiers | frontend
J4 | EPIC-J | Story | As an HR manager, publishing a new version re-triggers acknowledgement. |  |  | EPIC-J | Medium | 3 | 7 |  | M4 Open paid tiers | p2,m4
J4-T1 | J4 | Sub-task | Supersede trigger on new approved version |  |  |  | Medium |  | 4 | Database | M4 Open paid tiers | database
J4-T2 | J4 | Sub-task | Re-trigger behaviour tests |  |  |  | Medium |  | 3 | QA | M4 Open paid tiers | qa
J5 | EPIC-J | Story | As an HR manager, I can export the acknowledgement record to CSV. | One row per user per document version with timestamp. |  | EPIC-J | Medium | 2 | 5 |  | M4 Open paid tiers | p2,m4
J5-T1 | J5 | Sub-task | CSV export endpoint |  |  |  | Medium |  | 5 | Backend | M4 Open paid tiers | backend
EPIC-K |  | Epic | K — Billing & plans | Free, Pro and Team tiers with honest limit enforcement. | Billing & plans |  |  | 21 | 72 |  |  | epic
K1 | EPIC-K | Story | As a workspace, I start on Free with 3 users and 50 documents. | Free is capped on documents, not features, so AI value is visible before the paywall. |  | EPIC-K | High | 5 | 14 |  | M4 Open paid tiers | p1,m4
K1-T1 | K1 | Sub-task | subscriptions and usage_counters schema |  |  |  | High |  | 5 | Database | M4 Open paid tiers | database
K1-T2 | K1 | Sub-task | Default plan assignment on workspace creation |  |  |  | High |  | 3 | Backend | M4 Open paid tiers | backend
K1-T3 | K1 | Sub-task | Usage counting hooks across billable actions |  |  |  | High |  | 6 | Backend | M4 Open paid tiers | backend
K2 | EPIC-K | Story | As an admin, I can upgrade to Pro or Team and manage billing. |  |  | EPIC-K | High | 8 | 32 |  | M4 Open paid tiers | p1,m4
K2-T1 | K2 | Sub-task | Payment provider integration and webhooks |  |  |  | High |  | 14 | Backend | M4 Open paid tiers | backend
K2-T2 | K2 | Sub-task | Plan change, seat handling and proration |  |  |  | High |  | 8 | Backend | M4 Open paid tiers | backend
K2-T3 | K2 | Sub-task | Billing and usage screen (S22) |  |  |  | High |  | 10 | Frontend | M4 Open paid tiers | frontend
K3 | EPIC-K | Story | As a system, plan limits are enforced with a clear message, not a silent failure. | 429 with plan_limit_exceeded and the counter in details. |  | EPIC-K | High | 5 | 18 |  | M4 Open paid tiers | p1,m4
K3-T1 | K3 | Sub-task | Limit enforcement returning 429 across endpoints |  |  |  | High |  | 8 | Backend | M4 Open paid tiers | backend
K3-T2 | K3 | Sub-task | Approaching-limit notice in the app shell |  |  |  | High |  | 5 | Frontend | M4 Open paid tiers | frontend
K3-T3 | K3 | Sub-task | Per-tier limit enforcement tests |  |  |  | High |  | 5 | QA | M4 Open paid tiers | qa
K4 | EPIC-K | Story | As an admin, I can see usage against my plan limits. |  |  | EPIC-K | High | 3 | 8 |  | M4 Open paid tiers | p1,m4
K4-T1 | K4 | Sub-task | Usage endpoint returning counters against caps |  |  |  | High |  | 3 | Backend | M4 Open paid tiers | backend
K4-T2 | K4 | Sub-task | Usage-against-caps display |  |  |  | High |  | 5 | Frontend | M4 Open paid tiers | frontend
EPIC-L |  | Epic | L — Analytics & operations | Admin insight, review cadence and pipeline health. | Analytics & operations |  |  | 18 | 48 |  |  | epic
L1 | EPIC-L | Story | As an admin, I see documents by state, approval throughput and chat volume. |  |  | EPIC-L | Medium | 5 | 16 |  | M5 Scale | p2,m5
L1-T1 | L1 | Sub-task | Analytics aggregation queries |  |  |  | Medium |  | 8 | Backend | M5 Scale | backend
L1-T2 | L1 | Sub-task | Analytics section of insights screen (S20) |  |  |  | Medium |  | 8 | Frontend | M5 Scale | frontend
L2 | EPIC-L | Story | As an admin, I can see stale documents past their review date. |  |  | EPIC-L | Medium | 5 | 12 |  | M5 Scale | p2,m5
L2-T1 | L2 | Sub-task | review_due_at and workspace review cadence setting |  |  |  | Medium |  | 4 | Backend | M5 Scale | backend
L2-T2 | L2 | Sub-task | Past-review list and owner dashboard |  |  |  | Medium |  | 8 | Frontend | M5 Scale | frontend
L3 | EPIC-L | Story | As an operator, I'm alerted when an approved document has no current index entry. | Correctness invariant: approved implies indexed. |  | EPIC-L | Medium | 5 | 11 |  | M5 Scale | p2,m5
L3-T1 | L3 | Sub-task | Monitor job comparing approved documents to chunks |  |  |  | Medium |  | 6 | Infra | M5 Scale | infra
L3-T2 | L3 | Sub-task | Alert routing and runbook |  |  |  | Medium |  | 5 | Infra | M5 Scale | infra
L4 | EPIC-L | Story | As an operator, I can see cost per generated SOP by workspace. | Margin signal. Watch during design-partner phase before pricing decisions. |  | EPIC-L | Medium | 3 | 9 |  | M5 Scale | p2,m5
L4-T1 | L4 | Sub-task | LLM cost logging per workspace and job |  |  |  | Medium |  | 5 | Backend | M5 Scale | backend
L4-T2 | L4 | Sub-task | Internal cost-per-SOP view |  |  |  | Medium |  | 4 | Backend | M5 Scale | backend
EPIC-M |  | Epic | M — Platform & delivery | Design system, Aura theming, environments, CI/CD and observability. Prerequisites, not overhead. | Platform & delivery |  |  | 28 | 111 |  |  | epic
M1 | EPIC-M | Story | As a developer, I have design tokens and a component library so screens are consistent and fast to build. | Smaller than v1.0 assumed: PrimeNG supplies the generic controls. Document surfaces stay custom. |  | EPIC-M | Highest | 5 | 26 |  | M0 Foundation | p0,m0
M1-T1 | M1 | Sub-task | Token system: colour, type, spacing from screen spec |  |  |  | Highest |  | 8 | Design | M0 Foundation | design
M1-T2 | M1 | Sub-task | Custom document surfaces: reader, step list, control block, diff view |  |  |  | Highest |  | 14 | Frontend | M0 Foundation | frontend
M1-T3 | M1 | Sub-task | State pill component, word always present alongside colour |  |  |  | Highest |  | 4 | Frontend | M0 Foundation | frontend
M2 | EPIC-M | Story | As a developer, CI runs lint, type-check, tests and build on every push. |  |  | EPIC-M | Highest | 5 | 16 |  | M0 Foundation | p0,m0
M2-T1 | M2 | Sub-task | CI: Pint, PHPStan, PHPUnit, ESLint, Angular build |  |  |  | Highest |  | 8 | Infra | M0 Foundation | infra
M2-T2 | M2 | Sub-task | CD to staging on merge, production behind a manual gate |  |  |  | Highest |  | 8 | Infra | M0 Foundation | infra
M3 | EPIC-M | Story | As a developer, environments are separated and schema changes ship as versioned migrations. | No manual production SQL, ever. |  | EPIC-M | Highest | 5 | 25 |  | M0 Foundation | p0,m0
M3-T1 | M3 | Sub-task | App Platform spec in infra/do/app.yaml: web plus worker components |  |  |  | Highest |  | 10 | Infra | M0 Foundation | infra
M3-T2 | M3 | Sub-task | Managed MySQL and Valkey per environment with TLS enforced |  |  |  | Highest |  | 6 | Infra | M0 Foundation | infra
M3-T3 | M3 | Sub-task | Laravel migrations as a pre-deploy job, with rollback drill |  |  |  | Highest |  | 6 | Infra | M0 Foundation | infra
M3-T4 | M3 | Sub-task | FFmpeg in the worker image for frame extraction |  |  |  | Highest |  | 3 | Infra | M0 Foundation | infra
M4 | EPIC-M | Story | As an operator, I can see pipeline health and get alerted before users notice. |  |  | EPIC-M | High | 5 | 23 |  | M1 Prove the wedge | p1,m1
M4-T1 | M4 | Sub-task | Sentry SDK wired into Laravel and Angular with release tagging |  |  |  | High |  | 5 | Infra | M1 Prove the wedge | infra
M4-T2 | M4 | Sub-task | Structured logging per pipeline stage to stdout |  |  |  | High |  | 5 | Infra | M1 Prove the wedge | infra
M4-T3 | M4 | Sub-task | Metrics and dashboards: success rate, latency, cost per SOP |  |  |  | High |  | 8 | Infra | M1 Prove the wedge | infra
M4-T4 | M4 | Sub-task | Alerts: generation failures, embedding backlog, unindexed approved docs |  |  |  | High |  | 5 | Infra | M1 Prove the wedge | infra
M5 | EPIC-M | Story | As a developer, the PrimeNG Aura preset is configured to the Hub brand without colliding with document state. | Gold and draft amber share a hue family, and Aura paints primary across every control. Left at default this breaks the rule that colour means state. |  | EPIC-M | Highest | 8 | 21 |  | M0 Foundation | p0,m0
M5-T1 | M5 | Sub-task | Override Aura primary palette to navy #1E2761 |  |  |  | Highest |  | 6 | Frontend | M0 Foundation | frontend
M5-T2 | M5 | Sub-task | Map ice #CADCFC to selection and focus; confine gold to brand surfaces |  |  |  | Highest |  | 5 | Design | M0 Foundation | design
M5-T3 | M5 | Sub-task | Override Aura radius and density toward the controlled-document look |  |  |  | Highest |  | 6 | Frontend | M0 Foundation | frontend
M5-T4 | M5 | Sub-task | Verify review-blue pill against navy chrome and check AA contrast |  |  |  | Highest |  | 4 | QA | M0 Foundation | qa

## Epic Summary
Epic | Name | Stories | Tasks | Story Points | Estimate (h) | Estimate (days) | % of total
A | Foundation & tenancy | 5 | 20 | 31 | 145 | 24.1667 | 10.13%
B | Editor & document model | 7 | 21 | 40 | 163 | 27.1667 | 11.39%
C | Recording capture | 4 | 13 | 29 | 100 | 16.6667 | 6.988%
D | AI SOP generation | 6 | 22 | 52 | 195 | 32.5 | 13.63%
E | Governance | 6 | 18 | 34 | 123 | 20.5 | 8.595%
F | Permissions | 3 | 9 | 21 | 70 | 11.6667 | 4.892%
G | Search & retrieval | 6 | 19 | 47 | 155 | 25.8333 | 10.83%
H | Chatbot | 6 | 16 | 42 | 124 | 20.6667 | 8.665%
I | AI utilities | 4 | 10 | 26 | 67 | 11.1667 | 4.682%
J | Handbook & acknowledgements | 5 | 10 | 21 | 58 | 9.6667 | 4.053%
K | Billing & plans | 4 | 11 | 21 | 72 | 12 | 5.031%
L | Analytics & operations | 4 | 8 | 18 | 48 | 8 | 3.354%
M | Platform & delivery | 5 | 17 | 28 | 111 | 18.5 | 7.757%
| Total | 65 | 194 | 410 | 1431 | 238.5 | 100%
| Assumption — hours per working day | 6
| Assumption — team capacity, developer-days per week | 10
Estimates are engineering hours only. They exclude discovery, design partner support, recruitment and holiday.

## Milestone Plan
Milestone | Focus | Stories | Story Points | Estimate (h) | Estimate (days) | Elapsed weeks at capacity
M0 Foundation | Auth, tenancy, editor, design system, CI | 16 | 94 | 396 | 66 | 6.6
M1 Prove the wedge | Recording capture and AI SOP generation | 11 | 86 | 318 | 53 | 5.3
M2 Design partners | Governance and permissions, 5 partners onboarded | 9 | 55 | 193 | 32.1667 | 3.2167
M3 Retrieval layer | Search, chunking, chatbot with citations | 12 | 89 | 279 | 46.5 | 4.65
M4 Open paid tiers | AI utilities, handbook, billing | 13 | 68 | 197 | 32.8333 | 3.2833
M5 Scale | Analytics, review cadence, pipeline health | 4 | 18 | 48 | 8 | 0.8
| Total | 65 | 410 | 1431 | 238.5 | 23.85
Elapsed weeks assumes the capacity on Epic Summary and no parallelism between milestones. M2 and M3 overlap in the roadmap, so real elapsed time is shorter than this total.

## Component Load
Component | Tasks | Estimate (h) | % of build
AI/Pipeline | 24 | 232 | 16.21%
Backend | 58 | 373 | 26.07%
Database | 13 | 62 | 4.333%
Design | 5 | 30 | 2.096%
Frontend | 49 | 447 | 31.24%
Full stack | 5 | 32 | 2.236%
Infra | 16 | 98 | 6.848%
QA | 24 | 157 | 10.97%
Total | 194 | 1431 | 100%

## Import Guide
How to import this into Jira
1 | Save the 'Jira Import' sheet as CSV (File > Save As > CSV, that sheet only).
2 | In Jira: Settings > System > External System Import > CSV.
3 | Upload the CSV. On the field-mapping screen, map the columns as below.
4 | Tick 'Map field value' for Priority if your scheme uses different names.
5 | Import epics and stories first if your Jira rejects sub-tasks in one pass — filter Issue Type, import in two runs, then re-run with sub-tasks.
Column | Maps to
Issue ID | Issue ID (used only to link parents during import)
Parent ID | Parent ID
Issue Type | Issue Type
Summary | Summary
Description | Description
Epic Name | Epic Name (epics only)
Epic Link | Epic Link (stories only)
Priority | Priority
Story Points | Story Points (custom field)
Original Estimate (h) | Original Estimate — append 'h' or set the unit to hours
Component | Component/s — create these in the project first
Milestone | Sprint, Fix Version, or a custom field, whichever you use
Labels | Labels
Estimating basis
Story points | Carried from the product backlog document. They size relative complexity and are not converted from hours.
Task hours | Estimated per task, independently of points. Story hours are the sum of their sub-tasks, so points and hours are two separate views and will not correlate perfectly — that is intentional.
Excluded | Discovery, design-partner recruitment and support, project management, holiday, onboarding and rework after user feedback.
Confidence | Epics A, B, C, E, F, J, K and M are conventional work and estimate reliably. Epic D (generation) and Epic G/H (retrieval) contain genuine research risk — treat those hours as a first pass to be revised after the first ten real recordings.
Known correction
Epic B total | The product backlog document listed Epic B as 34 points. The stories in it actually sum to 40, and the backlog total is 367 rather than 361. This workbook uses the corrected figures and the backlog document has been updated to match.
Epic M is new | Design system, CI/CD, environments and observability were not in the original backlog. They are prerequisites rather than overhead, so they are estimated here.