## Jira Import
Issue ID | Parent ID | Issue Type | Summary | Description | Epic Name | Epic Link | Priority | Story Points | Original Estimate (h) | Component | Milestone | Labels | Status | Status note | Updated
EPIC-A |  | Epic | A — Foundation & tenancy | Auth, workspaces, spaces, folders and the application-layer scoping that isolates every tenant. | Foundation & tenancy | [6 empty] | epic | Done | 20/20 sub-tasks done, 5/5 stories done | 2026-09-22
A1 | EPIC-A | Story | As a new user, I can sign up and create a workspace so I have somewhere to put documents. | Email plus magic-link auth. Creating a workspace makes the creator its admin. |  | EPIC-A | Highest | 5 |  |  | M0 Foundation | p0,m0 | Done | 4/4 sub-tasks done | 2026-09-22
A1-T1 | A1 | Sub-task | Sanctum SPA session auth plus signed-URL magic links |  |  |  | Highest |  | 10 | Backend | M0 Foundation | backend | Done | Sanctum + signed magic links; b58a0df | 2026-09-22
A1-T2 | A1 | Sub-task | Build sign in / sign up screen (S1) |  |  |  | Highest |  | 8 | Frontend | M0 Foundation | frontend | Done | S1 | 2026-09-22
A1-T3 | A1 | Sub-task | Workspace creation flow with slug validation (S2) |  |  |  | Highest |  | 6 | Full stack | M0 Foundation | full-stack | Done | S2 | 2026-09-22
A1-T4 | A1 | Sub-task | Users table and workspace membership model |  |  |  | Highest |  | 4 | Database | M0 Foundation | database | Done | users, workspace_members | 2026-09-22
A2 | EPIC-A | Story | As an admin, I can invite teammates by email with a role so they can join the workspace. | Invite by email with a role assigned at invite time. |  | EPIC-A | Highest | 5 |  |  | M0 Foundation | p0,m0 | Done | 3/3 sub-tasks done | 2026-09-22
A2-T1 | A2 | Sub-task | Invite API with signed token and email delivery |  |  |  | Highest |  | 8 | Backend | M0 Foundation | backend | Done | Invite API + WorkspaceInviteNotification | 2026-09-22
A2-T2 | A2 | Sub-task | Invite and accept screens (S3) |  |  |  | Highest |  | 8 | Frontend | M0 Foundation | frontend | Done | S3 + accept | 2026-09-22
A2-T3 | A2 | Sub-task | Role assignment on invite acceptance |  |  |  | Highest |  | 4 | Backend | M0 Foundation | backend | Done |  | 2026-09-22
A3 | EPIC-A | Story | As a developer, every tenant table is workspace-scoped by default so no query can cross a workspace boundary. | Release blocker. MySQL has no row-level security, so the boundary is application-layer: a missed scope leaks rather than returning nothing. |  | EPIC-A | Highest | 13 |  |  | M0 Foundation | p0,m0 | Done | 7/7 sub-tasks done | 2026-09-22
A3-T1 | A3 | Sub-task | Build TenantModel base class with mandatory workspace global scope |  |  |  | Highest |  | 10 | Backend | M0 Foundation | backend | Done | TenantModel + TenantScope | 2026-09-22
A3-T2 | A3 | Sub-task | Auto-set workspace_id on create from request context, never from payload |  |  |  | Highest |  | 5 | Backend | M0 Foundation | backend | Done | workspace_id from CurrentWorkspace only | 2026-09-22
A3-T3 | A3 | Sub-task | Laravel Policies for space-level access |  |  |  | Highest |  | 10 | Backend | M0 Foundation | backend | Done | SpacePolicy/DocumentPolicy/RecordingPolicy | 2026-09-22
A3-T4 | A3 | Sub-task | Schema conformance test: every tenant table scoped, indexed, non-fillable |  |  |  | Highest |  | 12 | QA | M0 Foundation | qa | Done | SchemaConformanceTest | 2026-09-22
A3-T5 | A3 | Sub-task | Static analysis rule blocking raw unscoped queries |  |  |  | Highest |  | 6 | Infra | M0 Foundation | infra | Done | scripts/check-raw-queries.php | 2026-09-22
A3-T6 | A3 | Sub-task | Cross-tenant and cross-table consistency test suite |  |  |  | Highest |  | 14 | QA | M0 Foundation | qa | Done | CrossTenantIsolationTest | 2026-09-22
A3-T7 | A3 | Sub-task | Wire all gates into CI as blocking |  |  |  | Highest |  | 3 | Infra | M0 Foundation | infra | Done | ci.yml, all gates blocking | 2026-09-22
A4 | EPIC-A | Story | As an admin, I can create spaces and folders so documentation matches how the company is organised. | Workspace to space to folder, max depth 5. |  | EPIC-A | Highest | 5 |  |  | M0 Foundation | p0,m0 | Done | 3/3 sub-tasks done | 2026-09-22
A4-T1 | A4 | Sub-task | Schema and migrations for spaces and folders |  |  |  | Highest |  | 5 | Database | M0 Foundation | database | Done |  | 2026-09-22
A4-T2 | A4 | Sub-task | Folder CRUD API including move with depth check |  |  |  | Highest |  | 8 | Backend | M0 Foundation | backend | Done | depth ≤ 5, delete strategy | 2026-09-22
A4-T3 | A4 | Sub-task | Sidebar tree and space browser (S5, S6) |  |  |  | Highest |  | 10 | Frontend | M0 Foundation | frontend | Done | S5, S6 | 2026-09-22
A5 | EPIC-A | Story | As a user, I see only the spaces I'm a member of, everywhere in the product. | No greyed-out items hinting at content behind a permission wall. |  | EPIC-A | Highest | 3 |  |  | M0 Foundation | p0,m0 | Done | 3/3 sub-tasks done | 2026-09-22
A5-T1 | A5 | Sub-task | Scope sidebar and browser to accessible spaces |  |  |  | Highest |  | 5 | Frontend | M0 Foundation | frontend | Done |  | 2026-09-22
A5-T2 | A5 | Sub-task | Return 403 not 404 so existence is never leaked |  |  |  | Highest |  | 5 | Backend | M0 Foundation | backend | Done | ResolveWorkspace + bootstrap 404→403 | 2026-09-22
A5-T3 | A5 | Sub-task | Permission visibility tests across surfaces |  |  |  | Highest |  | 4 | QA | M0 Foundation | qa | Done |  | 2026-09-22
EPIC-B |  | Epic | B — Editor & document model | The block editor, the structured SOP model, templates and paste fidelity. | Editor & document model | [6 empty] | epic | Done | 21/21 sub-tasks done, 7/7 stories done | 2026-09-23
B1 | EPIC-B | Story | As an editor, I can write a document with headings, lists, tables, callouts and images. | Content stored as structured JSON, never HTML, so diffing and chunking stay reliable. |  | EPIC-B | Highest | 13 |  |  | M0 Foundation | p0,m0 | Done | 5/5 sub-tasks done | 2026-09-23
B1-T1 | B1 | Sub-task | Editor foundation and structured JSON document model |  |  |  | Highest |  | 20 | Frontend | M0 Foundation | frontend | Done | structured JSON Content model | 2026-09-22
B1-T2 | B1 | Sub-task | Core blocks: headings, lists, tables, callouts, code |  |  |  | Highest |  | 20 | Frontend | M0 Foundation | frontend | Done | block-editor: all F2 types, slash menu; 44e896b | 2026-09-22
B1-T3 | B1 | Sub-task | Image upload to object storage, referenced by ID |  |  |  | Highest |  | 10 | Full stack | M0 Foundation | full-stack | Done | editor images/files: presigned PUT, complete, signed URL after policy check; paste/drop upload; commit pending | 2026-09-23
B1-T4 | B1 | Sub-task | Reader render parity with editor |  |  |  | Highest |  | 8 | Frontend | M0 Foundation | frontend | Done | reader renders every block type | 2026-09-22
B1-T5 | B1 | Sub-task | Round-trip save/load fidelity tests |  |  |  | Highest |  | 6 | QA | M0 Foundation | qa | Done | EditorCompletionTest: every block type round-trips exactly; unknown types rejected; commit pending | 2026-09-23
B2 | EPIC-B | Story | As an editor, my work autosaves so I never lose a draft. | Debounced at 2s with an explicit saved indicator, never a spinner. |  | EPIC-B | Highest | 3 |  |  | M0 Foundation | p0,m0 | Done | 3/3 sub-tasks done | 2026-09-23
B2-T1 | B2 | Sub-task | Debounced autosave and saved-state indicator |  |  |  | Highest |  | 6 | Frontend | M0 Foundation | frontend | Done | 2 s debounce, Saved hh:mm | 2026-09-22
B2-T2 | B2 | Sub-task | Optimistic concurrency via expected_updated_at and 409 |  |  |  | Highest |  | 6 | Backend | M0 Foundation | backend | Done | expected_updated_at → 409 | 2026-09-22
B2-T3 | B2 | Sub-task | Mid-edit tab close recovery test |  |  |  | Highest |  | 2 | QA | M0 Foundation | qa | Done | DraftBackup (local copy + restore only when server copy unchanged), keepalive PATCH on pagehide, beforeunload warning; spec; commit pending | 2026-09-23
B3 | EPIC-B | Story | As an editor, I can build an SOP with structured steps I can reorder and renumber automatically. | Steps are rows as well as content, so they can be cited by ID. |  | EPIC-B | Highest | 8 |  |  | M0 Foundation | p0,m0 | Done | 4/4 sub-tasks done | 2026-09-23
B3-T1 | B3 | Sub-task | document_steps schema and step CRUD API |  |  |  | Highest |  | 8 | Backend | M0 Foundation | backend | Done |  | 2026-09-22
B3-T2 | B3 | Sub-task | Step editor with drag reorder and live renumber (S8) |  |  |  | Highest |  | 14 | Frontend | M0 Foundation | frontend | Done | CDK drag-drop with handle for steps and blocks; live renumber; arrows kept for keyboard; commit pending | 2026-09-23
B3-T3 | B3 | Sub-task | Block submit when a SOP has zero steps |  |  |  | Highest |  | 3 | Backend | M0 Foundation | backend | Done | submit-check | 2026-09-22
B3-T4 | B3 | Sub-task | Reorder and renumber correctness tests |  |  |  | Highest |  | 3 | QA | M0 Foundation | qa | Done |  | 2026-09-22
B4 | EPIC-B | Story | As an editor, I can mark a step critical or a checkpoint so readers see what matters. | Critical steps always appear in chatbot answers about that process. |  | EPIC-B | High | 3 |  |  | M0 Foundation | p1,m0 | Done | 2/2 sub-tasks done | 2026-09-22
B4-T1 | B4 | Sub-task | Add critical and checkpoint flags to schema and API |  |  |  | High |  | 3 | Backend | M0 Foundation | backend | Done |  | 2026-09-22
B4-T2 | B4 | Sub-task | Editor controls and reader amber-rule treatment |  |  |  | High |  | 7 | Frontend | M0 Foundation | frontend | Done |  | 2026-09-22
B5 | EPIC-B | Story | As an editor, I can start from a template (blank, onboarding, playbook, policy). | Workspaces can also save their own templates. |  | EPIC-B | High | 5 |  |  | M0 Foundation | p1,m0 | Done | 3/3 sub-tasks done | 2026-09-23
B5-T1 | B5 | Sub-task | Template storage and four seeded templates |  |  |  | High |  | 6 | Backend | M0 Foundation | backend | Done | four seeded templates | 2026-09-22
B5-T2 | B5 | Sub-task | Template picker and create-from-template flow |  |  |  | High |  | 8 | Frontend | M0 Foundation | frontend | Done | space browser create-from-template | 2026-09-22
B5-T3 | B5 | Sub-task | Workspace-defined custom templates |  |  |  | High |  | 5 | Full stack | M0 Foundation | full-stack | Done | document_templates; save from document, grouped picker, delete by creator/admin; commit pending | 2026-09-23
B6 | EPIC-B | Story | As an editor, I can paste from Google Docs or Notion without losing structure. | Headings, lists and tables must survive, including nesting. |  | EPIC-B | High | 5 |  |  | M0 Foundation | p1,m0 | Done | 2/2 sub-tasks done | 2026-09-23
B6-T1 | B6 | Sub-task | Paste transformer for headings, lists and tables |  |  |  | High |  | 12 | Frontend | M0 Foundation | frontend | Done | paste.ts: plain text + HTML (Word/Docs/Confluence) | 2026-09-22
B6-T2 | B6 | Sub-task | Nested list and table fidelity tests across sources |  |  |  | High |  | 5 | QA | M0 Foundation | qa | Done | nested lists (levels) from plain text, Notion, Google Docs, Word; ragged/colspan tables; spec; commit pending | 2026-09-23
B7 | EPIC-B | Story | As an editor, I can link to another internal document. | Cross-linking replaces multi-filing; a document lives in one folder. |  | EPIC-B | High | 3 |  |  | M0 Foundation | p1,m0 | Done | 2/2 sub-tasks done | 2026-09-23
B7-T1 | B7 | Sub-task | Internal link block and document picker |  |  |  | High |  | 7 | Frontend | M0 Foundation | frontend | Done | link-to-document block with title search picker; commit pending | 2026-09-23
B7-T2 | B7 | Sub-task | Backlink resolution and broken-link handling |  |  |  | High |  | 4 | Backend | M0 Foundation | backend | Done | document_links graph, backlinks in reader, unavailable state for deleted/forbidden targets; commit pending | 2026-09-23
EPIC-C |  | Epic | C — Recording capture | Browser screen capture, resumable upload and honest pipeline status. | Recording capture | [6 empty] | epic | Done | 13/13 sub-tasks done, 4/4 stories done | 2026-09-23
C1 | EPIC-C | Story | As a contributor, I can record my screen and voice in the browser and upload it. | Browser capture only for v1. Half of the wedge. |  | EPIC-C | Highest | 13 |  |  | M1 Prove the wedge | p0,m1 | Done | 5/5 sub-tasks done | 2026-09-23
C1-T1 | C1 | Sub-task | Screen and mic capture via getDisplayMedia and MediaRecorder |  |  |  | Highest |  | 14 | Frontend | M1 Prove the wedge | frontend | Done | record-modal | 2026-09-22
C1-T2 | C1 | Sub-task | Permission primer before the browser prompt (S11) |  |  |  | Highest |  | 5 | Design | M1 Prove the wedge | design | Done | S11 primer | 2026-09-22
C1-T3 | C1 | Sub-task | Presigned S3 multipart upload direct to Spaces via Flysystem |  |  |  | Highest |  | 10 | Backend | M1 Prove the wedge | backend | Done | SpacesStorage presigned multipart | 2026-09-22
C1-T4 | C1 | Sub-task | recordings schema and upload registration endpoint |  |  |  | Highest |  | 6 | Backend | M1 Prove the wedge | backend | Done |  | 2026-09-22
C1-T5 | C1 | Sub-task | Cross-browser capture verification (Chrome, Edge, Firefox, Safari) |  |  |  | Highest |  | 8 | QA | M1 Prove the wedge | qa | Done | Safari MP4 labelling fixed; per-browser format + matrix spec; Chromium capture PASS (automated, web/e2e/capture-probe); Edge/Firefox/Safari confirmed complete by project lead 2026-09-23 (results not recorded in the probe README) | 2026-09-23
C2 | EPIC-C | Story | As a contributor, I can drag and drop an existing recording file. | Accepts webm, mp4, mov up to 60 minutes and 2 GB. |  | EPIC-C | Highest | 3 |  |  | M1 Prove the wedge | p0,m1 | Done | 2/2 sub-tasks done | 2026-09-22
C2-T1 | C2 | Sub-task | Drop zone with format and size validation |  |  |  | Highest |  | 6 | Frontend | M1 Prove the wedge | frontend | Done |  | 2026-09-22
C2-T2 | C2 | Sub-task | Server-side format and limit validation |  |  |  | Highest |  | 3 | Backend | M1 Prove the wedge | backend | Done |  | 2026-09-22
C3 | EPIC-C | Story | As a contributor, my upload resumes after a network interruption. | A 45-minute upload must survive one dropped connection. |  | EPIC-C | Highest | 8 |  |  | M1 Prove the wedge | p0,m1 | Done | 3/3 sub-tasks done | 2026-09-23
C3-T1 | C3 | Sub-task | Chunked upload with retry and resume |  |  |  | Highest |  | 14 | Frontend | M1 Prove the wedge | frontend | Done | resume after reload: GET /recordings/{id}/upload (ListParts + re-signed URLs), IndexedDB session (recording video kept locally; files re-picked and fingerprint-checked), Unfinished uploads panel, offline wait; stale uploads aborted after 7 days | 2026-09-23
C3-T2 | C3 | Sub-task | Multipart completion and integrity check |  |  |  | Highest |  | 8 | Backend | M1 Prove the wedge | backend | Done |  | 2026-09-22
C3-T3 | C3 | Sub-task | Interrupted-network upload test |  |  |  | Highest |  | 6 | QA | M1 Prove the wedge | qa | Done | resumable-upload.spec (network drop → reload → only missing parts sent; server-authoritative parts; file mismatch; offline wait) + ResumableUploadTest (API) | 2026-09-23
C4 | EPIC-C | Story | As a contributor, I can see the processing status of my recording at every stage. | Determinate progress, and failures that say what to do next. |  | EPIC-C | Highest | 5 |  |  | M1 Prove the wedge | p0,m1 | Done | 3/3 sub-tasks done | 2026-09-22
C4-T1 | C4 | Sub-task | pipeline_jobs table and status transitions |  |  |  | Highest |  | 6 | Backend | M1 Prove the wedge | backend | Done |  | 2026-09-22
C4-T2 | C4 | Sub-task | Status polling and recordings list (S10); Reverb deferred to M3 |  |  |  | Highest |  | 10 | Frontend | M1 Prove the wedge | frontend | Done | S10 polling | 2026-09-22
C4-T3 | C4 | Sub-task | Plain-language failure reasons with retry |  |  |  | Highest |  | 4 | Full stack | M1 Prove the wedge | full-stack | Done | PipelineFailed reasons | 2026-09-22
EPIC-D |  | Epic | D — AI SOP generation | The wedge. Recording in, structured draft procedure out. | AI SOP generation | [6 empty] | epic | In Progress | 17/22 sub-tasks done, 3/6 stories done; the rest need real recordings / provider keys | 2026-09-23
D0 | EPIC-D | Story | As a team, we've chosen a transcription provider on evidence from real recordings. | The Claude API has no speech-to-text endpoint, so the stack does not yet include one. Blocks the wedge. |  | EPIC-D | Highest | 5 |  |  | M1 Prove the wedge | p0,m1 | Blocked | 0/3 sub-tasks done | 2026-09-22
D0-T1 | D0 | Sub-task | Assemble 10-recording evaluation set spanning length, accent and noise |  |  |  | Highest |  | 5 | QA | M1 Prove the wedge | qa | Blocked | needs 10 real recordings from the team | 2026-09-22
D0-T2 | D0 | Sub-task | Benchmark Whisper API and Deepgram on timestamp accuracy and cost |  |  |  | Highest |  | 10 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Blocked | harness ready: pipeline:eval --providers=whisper,deepgram; needs recordings + provider keys | 2026-09-23
D0-T3 | D0 | Sub-task | Confirm zero-retention terms with the chosen provider |  |  |  | Highest |  | 3 | Backend | M1 Prove the wedge | backend | Blocked | after provider choice | 2026-09-22
D1 | EPIC-D | Story | As a system, I transcribe an uploaded recording with word-level timestamps. | Halts with a clear message on very low confidence rather than inventing content. |  | EPIC-D | Highest | 8 |  |  | M1 Prove the wedge | p0,m1 | Done | 4/4 sub-tasks done | 2026-09-22
D1-T1 | D1 | Sub-task | Speech-to-text adapter interface and provider implementation |  |  |  | Highest |  | 10 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done | Transcriber driver: whisper, deepgram, fake, null | 2026-09-22
D1-T2 | D1 | Sub-task | transcripts schema with word-level timestamps |  |  |  | Highest |  | 5 | Database | M1 Prove the wedge | database | Done |  | 2026-09-22
D1-T3 | D1 | Sub-task | Retry policy and low-confidence halt |  |  |  | Highest |  | 6 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done |  | 2026-09-22
D1-T4 | D1 | Sub-task | Job idempotency via job_key |  |  |  | Highest |  | 5 | Backend | M1 Prove the wedge | backend | Done | job_key + ShouldBeUnique | 2026-09-22
D2 | EPIC-D | Story | As a system, I segment the transcript into distinct actions. | Falls back to paragraph segmentation if action detection fails. |  | EPIC-D | Highest | 13 |  |  | M1 Prove the wedge | p0,m1 | In Progress | 3/4 sub-tasks done | 2026-09-23
D2-T1 | D2 | Sub-task | Transcript cue and pause-based segmentation |  |  |  | Highest |  | 16 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done | LLM segmentation ([segment] prompt) | 2026-09-22
D2-T2 | D2 | Sub-task | Visual scene-change detection |  |  |  | Highest |  | 14 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done | FFmpeg scene detection (Vision::sceneChanges); model sees screen changes; boundaries within 2 s snap to them; fallback splits at them | 2026-09-23
D2-T3 | D2 | Sub-task | Segment merge logic and paragraph fallback |  |  |  | Highest |  | 8 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done | halt with reason when no process | 2026-09-22
D2-T4 | D2 | Sub-task | Segmentation accuracy eval on 20 real recordings |  |  |  | Highest |  | 10 | QA | M1 Prove the wedge | qa | Blocked | scoring done: segments-review.csv boundary precision/recall/F1 ±2 s; needs 20 real recordings | 2026-09-23
D3 | EPIC-D | Story | As a system, I extract one deduplicated key frame per detected action. | Continues without screenshots rather than failing the whole generation. |  | EPIC-D | Highest | 8 |  |  | M1 Prove the wedge | p0,m1 | Done | 3/3 sub-tasks done | 2026-09-23
D3-T1 | D3 | Sub-task | Frame extraction per segment via ffmpeg |  |  |  | Highest |  | 10 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done | ffmpeg midpoint frame | 2026-09-22
D3-T2 | D3 | Sub-task | Perceptual dedup of near-identical frames |  |  |  | Highest |  | 8 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done | 64-bit difference hash via FFmpeg, Hamming ≤ 6 bits = same screen; frame taken after the screen settles | 2026-09-23
D3-T3 | D3 | Sub-task | Store frames as media_assets with step linkage |  |  |  | Highest |  | 6 | Backend | M1 Prove the wedge | backend | Done |  | 2026-09-22
D4 | EPIC-D | Story | As a contributor, a structured draft SOP is generated with purpose, scope, numbered steps, screenshots and outcome. | Always a draft. Never auto-approved, never auto-indexed. |  | EPIC-D | Highest | 13 |  |  | M1 Prove the wedge | p0,m1 | In Progress | 4/5 sub-tasks done | 2026-09-23
D4-T1 | D4 | Sub-task | Generation prompt and structured output schema |  |  |  | Highest |  | 16 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done | [generate] prompt, JSON schema | 2026-09-22
D4-T2 | D4 | Sub-task | Per-segment transcript summarisation for cost control |  |  |  | Highest |  | 8 | AI/Pipeline | M1 Prove the wedge | ai-pipeline | Done | DraftWriter digests long transcripts per segment in batches ([digest] prompt) before generation; raw words kept where a digest fails | 2026-09-23
D4-T3 | D4 | Sub-task | Draft document and step assembly from model output |  |  |  | Highest |  | 10 | Backend | M1 Prove the wedge | backend | Done |  | 2026-09-22
D4-T4 | D4 | Sub-task | Re-run creates a new draft and never overwrites edits |  |  |  | Highest |  | 6 | Backend | M1 Prove the wedge | backend | Done | regenerate creates a new draft | 2026-09-22
D4-T5 | D4 | Sub-task | Generation eval set and scoring harness (20 recordings) |  |  |  | Highest |  | 12 | QA | M1 Prove the wedge | qa | Blocked | harness done: php artisan pipeline:eval + score.py, 20-slot eval-set.csv; needs the 20 real recordings | 2026-09-23
D5 | EPIC-D | Story | As a contributor, each generated step links back to its timestamp in the recording so I can verify it. | Submit stays disabled until every step is verified or edited. |  | EPIC-D | Highest | 5 |  |  | M1 Prove the wedge | p0,m1 | Done | 3/3 sub-tasks done | 2026-09-22
D5-T1 | D5 | Sub-task | Persist source timestamps on generated steps |  |  |  | Highest |  | 3 | Backend | M1 Prove the wedge | backend | Done |  | 2026-09-22
D5-T2 | D5 | Sub-task | Draft review screen with bound scrubber and steps (S9) |  |  |  | Highest |  | 16 | Frontend | M1 Prove the wedge | frontend | Done | S9 | 2026-09-22
D5-T3 | D5 | Sub-task | Verify control and submit gating |  |  |  | Highest |  | 8 | Frontend | M1 Prove the wedge | frontend | Done | FR-315 gating | 2026-09-22
EPIC-E |  | Epic | E — Governance | Approval workflow, versioning, diffs and the audit trail. | Governance | [6 empty] | epic | Done | 18/18 sub-tasks done, 6/6 stories done | 2026-09-22
E1 | EPIC-E | Story | As an owner, I can submit a draft for review and approve or request changes. | Self-approval is off by default. Request changes needs a comment. |  | EPIC-E | High | 8 |  |  | M2 Design partners | p1,m2 | Done | 4/4 sub-tasks done | 2026-09-22
E1-T1 | E1 | Sub-task | Approval state machine and transition guards |  |  |  | High |  | 8 | Backend | M2 Design partners | backend | Done | Workflow | 2026-09-22
E1-T2 | E1 | Sub-task | Self-approval workspace setting enforcement |  |  |  | High |  | 3 | Backend | M2 Design partners | backend | Done |  | 2026-09-22
E1-T3 | E1 | Sub-task | Approval review screen, diff as default view (S12) |  |  |  | High |  | 12 | Frontend | M2 Design partners | frontend | Done | S12 | 2026-09-22
E1-T4 | E1 | Sub-task | In-app and email review notifications |  |  |  | High |  | 7 | Full stack | M2 Design partners | full-stack | Done |  | 2026-09-22
E2 | EPIC-E | Story | As a reader, I see an approved-by and version badge so I know I can trust it. | The control block above the title. |  | EPIC-E | High | 3 |  |  | M2 Design partners | p1,m2 | Done | 2/2 sub-tasks done | 2026-09-22
E2-T1 | E2 | Sub-task | Control block in document reader (S7) |  |  |  | High |  | 6 | Frontend | M2 Design partners | frontend | Done | S7 control block | 2026-09-22
E2-T2 | E2 | Sub-task | Expose version and approver metadata via API |  |  |  | High |  | 3 | Backend | M2 Design partners | backend | Done |  | 2026-09-22
E3 | EPIC-E | Story | As an owner, editing an approved document creates a new draft while the approved version stays live. | The most misunderstood behaviour in the product. Needs an on-screen banner. |  | EPIC-E | High | 8 |  |  | M2 Design partners | p1,m2 | Done | 4/4 sub-tasks done | 2026-09-22
E3-T1 | E3 | Sub-task | Trigger: edit after approval flips state to draft |  |  |  | High |  | 6 | Database | M2 Design partners | database | Done |  | 2026-09-22
E3-T2 | E3 | Sub-task | Split working copy from approved version in API |  |  |  | High |  | 10 | Backend | M2 Design partners | backend | Done | /published vs working copy | 2026-09-22
E3-T3 | E3 | Sub-task | Editor banner explaining the live version (S8) |  |  |  | High |  | 5 | Frontend | M2 Design partners | frontend | Done |  | 2026-09-22
E3-T4 | E3 | Sub-task | Draft-vs-live behaviour tests |  |  |  | High |  | 6 | QA | M2 Design partners | qa | Done |  | 2026-09-22
E4 | EPIC-E | Story | As an owner, I can see the full version history and a block-level diff between any two versions. | Moved blocks marked as moved, not as a delete plus an add. |  | EPIC-E | High | 8 |  |  | M2 Design partners | p1,m2 | Done | 3/3 sub-tasks done | 2026-09-22
E4-T1 | E4 | Sub-task | document_versions schema and numbering trigger |  |  |  | High |  | 6 | Database | M2 Design partners | database | Done | row lock + unique key instead of trigger | 2026-09-22
E4-T2 | E4 | Sub-task | Block-level diff algorithm including move detection |  |  |  | High |  | 16 | Backend | M2 Design partners | backend | Done | Diff with move detection | 2026-09-22
E4-T3 | E4 | Sub-task | Version history and diff screen (S13) |  |  |  | High |  | 12 | Frontend | M2 Design partners | frontend | Done | S13 | 2026-09-22
E5 | EPIC-E | Story | As an owner, I can restore an old version as a new draft. | Restore never overwrites the live approved version. |  | EPIC-E | High | 3 |  |  | M2 Design partners | p1,m2 | Done | 2/2 sub-tasks done | 2026-09-22
E5-T1 | E5 | Sub-task | Restore endpoint creating a draft |  |  |  | High |  | 4 | Backend | M2 Design partners | backend | Done |  | 2026-09-22
E5-T2 | E5 | Sub-task | Restore confirmation stating the consequence |  |  |  | High |  | 3 | Frontend | M2 Design partners | frontend | Done |  | 2026-09-22
E6 | EPIC-E | Story | As an admin, every state change is written to an append-only audit log. | Insert and select grants only. No update, no delete. |  | EPIC-E | High | 4 |  |  | M2 Design partners | p1,m2 | Done | 3/3 sub-tasks done | 2026-09-22
E6-T1 | E6 | Sub-task | audit_log table with append-only grants |  |  |  | High |  | 4 | Database | M2 Design partners | database | Done | grant revocation is a DBA step (documented) | 2026-09-22
E6-T2 | E6 | Sub-task | Audit write triggers for state and permission changes |  |  |  | High |  | 6 | Backend | M2 Design partners | backend | Done | Audit::record at every state/permission change | 2026-09-22
E6-T3 | E6 | Sub-task | Audit log screen with export (S21) |  |  |  | High |  | 6 | Frontend | M2 Design partners | frontend | Done | S21; 3fb9d6c | 2026-09-22
EPIC-F |  | Epic | F — Permissions | Roles, folder overrides and immediate revocation. | Permissions | [6 empty] | epic | Done | 9/9 sub-tasks done, 3/3 stories done | 2026-09-22
F1 | EPIC-F | Story | As an admin, I can assign admin, approver, editor, reader and guest roles per space. | Space is the primary permission boundary. |  | EPIC-F | High | 8 |  |  | M2 Design partners | p1,m2 | Done | 4/4 sub-tasks done | 2026-09-22
F1-T1 | F1 | Sub-task | space_members schema and role enum |  |  |  | High |  | 4 | Database | M2 Design partners | database | Done |  | 2026-09-22
F1-T2 | F1 | Sub-task | Role assignment API with transition guards |  |  |  | High |  | 8 | Backend | M2 Design partners | backend | Done | last-admin rule | 2026-09-22
F1-T3 | F1 | Sub-task | Members and roles screen (S18) |  |  |  | High |  | 10 | Frontend | M2 Design partners | frontend | Done | S18 | 2026-09-22
F1-T4 | F1 | Sub-task | Consequence-stating confirmation copy |  |  |  | High |  | 4 | Design | M2 Design partners | design | Done |  | 2026-09-22
F2 | EPIC-F | Story | As an admin, I can override permissions at folder level and inspect the effective result per user. | Permission bugs are comprehension failures; the inspector is the fix. |  | EPIC-F | High | 8 |  |  | M2 Design partners | p1,m2 | Done | 3/3 sub-tasks done | 2026-09-22
F2-T1 | F2 | Sub-task | Folder override model and resolution logic |  |  |  | High |  | 12 | Backend | M2 Design partners | backend | Done | folder_permissions + Access::resolve | 2026-09-22
F2-T2 | F2 | Sub-task | Effective permission inspector (S19) |  |  |  | High |  | 12 | Frontend | M2 Design partners | frontend | Done | S19 inspector with chain | 2026-09-22
F2-T3 | F2 | Sub-task | Resolution correctness test matrix |  |  |  | High |  | 6 | QA | M2 Design partners | qa | Done | FolderPermissionTest | 2026-09-22
F3 | EPIC-F | Story | As an admin, removing someone's access immediately removes those documents from their search and chat. | No cache window in which a removed user still gets answers. |  | EPIC-F | High | 5 |  |  | M2 Design partners | p1,m2 | Done | 2/2 sub-tasks done | 2026-09-22
F3-T1 | F3 | Sub-task | Synchronous retrieval-scope update on membership change |  |  |  | High |  | 8 | Backend | M2 Design partners | backend | Done | scope built per query from live membership | 2026-09-22
F3-T2 | F3 | Sub-task | No-cache-window revocation verification test |  |  |  | High |  | 6 | QA | M2 Design partners | qa | Done | RetrievalTest | 2026-09-22
EPIC-G |  | Epic | G — Search & retrieval | Provider selection, chunking, embedding, hybrid ranking and in-query permission filtering. | Search & retrieval | [6 empty] | epic | In Progress | 16/19 sub-tasks done, 3/6 stories done; the rest need the DO droplet and design-partner content | 2026-09-23
G0 | EPIC-G | Story | As a team, we've chosen an embeddings provider and a vector store, and proven them on real content. | Claude has no embeddings endpoint and MySQL 8.4 has no VECTOR type. Both are open decisions. |  | EPIC-G | High | 5 |  |  | M3 Retrieval layer | p1,m3 | In Progress | 2/3 sub-tasks done | 2026-09-23
G0-T1 | G0 | Sub-task | Benchmark Voyage AI and OpenAI embeddings on the retrieval eval set |  |  |  | High |  | 10 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | decided without benchmark: OpenAI text-embedding-3-small (user decision 21 Sep) | 2026-09-22
G0-T2 | G0 | Sub-task | Stand up Qdrant on DigitalOcean and compare against managed Pinecone |  |  |  | High |  | 8 | Infra | M3 Retrieval layer | infra | Blocked | done: infra/qdrant (compose, Caddy TLS, backups, cloud-init, runbook) + QdrantStore integration test vs real Qdrant 1.19.1 in CI; Pinecone comparison superseded by the 21 Sep decision. Needs: droplet created in the DO account | 2026-09-23
G0-T3 | G0 | Sub-task | Record embed_model per chunk so a provider change is a targetable re-embed |  |  |  | High |  | 3 | Backend | M3 Retrieval layer | backend | Done | embed_model on document_chunks | 2026-09-22
G1 | EPIC-G | Story | As a system, I chunk approved documents by step and section and embed them on approval. | Chunking on semantic boundaries, not fixed token windows. Runs on approval only. |  | EPIC-G | High | 13 |  |  | M3 Retrieval layer | p1,m3 | Done | 5/5 sub-tasks done | 2026-09-23
G1-T1 | G1 | Sub-task | Semantic chunking by step and section |  |  |  | High |  | 12 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | Chunker | 2026-09-22
G1-T2 | G1 | Sub-task | document_chunks schema with section_ref |  |  |  | High |  | 5 | Database | M3 Retrieval layer | database | Done |  | 2026-09-22
G1-T3 | G1 | Sub-task | Embedding job and vector upsert on approval |  |  |  | High |  | 10 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | IndexDocument on approval | 2026-09-22
G1-T4 | G1 | Sub-task | Vector store adapter (Pinecone or Qdrant) |  |  |  | High |  | 10 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | QdrantStore + FakeVectorStore | 2026-09-22
G1-T5 | G1 | Sub-task | Unindexed-approved-document monitor and alert |  |  |  | High |  | 6 | Infra | M3 Retrieval layer | infra | Done | retrieval:check-index every 10 min: re-queues, alerts (error log + admin notice), removes stray chunks; unindexed list on /admin/insights | 2026-09-23
G2 | EPIC-G | Story | As a user, I can search by meaning and find documents phrased differently from my query. | p95 under 800ms on a 5,000-document workspace. |  | EPIC-G | High | 8 |  |  | M3 Retrieval layer | p1,m3 | In Progress | 2/3 sub-tasks done | 2026-09-23
G2-T1 | G2 | Sub-task | Query embedding and vector search path |  |  |  | High |  | 8 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | Retriever | 2026-09-22
G2-T2 | G2 | Sub-task | Search results screen (S14) |  |  |  | High |  | 10 | Frontend | M3 Retrieval layer | frontend | Done | S14 | 2026-09-22
G2-T3 | G2 | Sub-task | Relevance eval set of 50 query/document pairs |  |  |  | High |  | 6 | QA | M3 Retrieval layer | qa | Blocked | harness done: php artisan retrieval:eval + spike/retrieval-eval format; needs design-partner content for the 50 + 15 questions | 2026-09-23
G3 | EPIC-G | Story | As a user, results are hybrid-ranked across semantic and keyword matching. | Reciprocal rank fusion over vector and full-text results. |  | EPIC-G | High | 8 |  |  | M3 Retrieval layer | p1,m3 | In Progress | 2/3 sub-tasks done | 2026-09-23
G3-T1 | G3 | Sub-task | MySQL FULLTEXT index, custom stopwords, min token size config |  |  |  | High |  | 10 | Backend | M3 Retrieval layer | backend | Done | InnoDB FULLTEXT ft_chunk_search + custom stopword table via session variable (migration 001500); verified on MySQL 8.4; LIKE fallback on SQLite | 2026-09-23
G3-T2 | G3 | Sub-task | Reciprocal rank fusion by position, not raw score, with weight tuning |  |  |  | High |  | 12 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | RRF 1.0/0.6 | 2026-09-22
G3-T3 | G3 | Sub-task | Ranking quality eval |  |  |  | High |  | 6 | QA | M3 Retrieval layer | qa | Blocked | harness done: retrieval:eval compares fusion weights side by side; needs the eval set (G2-T3) | 2026-09-23
G4 | EPIC-G | Story | As a user, I can filter results by space, owner, type and date. |  |  | EPIC-G | High | 5 |  |  | M3 Retrieval layer | p1,m3 | Done | 2/2 sub-tasks done | 2026-09-23
G4-T1 | G4 | Sub-task | Filter parameters on search API |  |  |  | High |  | 5 | Backend | M3 Retrieval layer | backend | Done | space, doc_type, owner, approved_after/before — applied inside both legs | 2026-09-23
G4-T2 | G4 | Sub-task | Filter rail UI |  |  |  | High |  | 8 | Frontend | M3 Retrieval layer | frontend | Done | space, type, owner (me), approval period | 2026-09-23
G5 | EPIC-G | Story | As a system, retrieval filters by permission inside the query, never after. | Release blocker. Two independent checks must both fail for a leak to occur. |  | EPIC-G | High | 8 |  |  | M3 Retrieval layer | p1,m3 | Done | 3/3 sub-tasks done | 2026-09-23
G5-T1 | G5 | Sub-task | Workspace, space and state metadata filters on vector query |  |  |  | High |  | 8 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done |  | 2026-09-22
G5-T2 | G5 | Sub-task | Policy-backed chunk scoping in the query layer |  |  |  | High |  | 6 | Backend | M3 Retrieval layer | backend | Done |  | 2026-09-22
G5-T3 | G5 | Sub-task | Adversarial retrieval leak tests including existence probing |  |  |  | High |  | 12 | QA | M3 Retrieval layer | qa | Done | AdversarialRetrievalTest: 7 probes (search, chat, filters, id routes, links, folders, drafts/archive, cross-workspace); found and fixed: documents under revision vanished from search | 2026-09-23
EPIC-H |  | Epic | H — Chatbot | Answers from approved content only, cited, with designed refusal. | Chatbot | [6 empty] | epic | In Progress | 15/16 sub-tasks done, 5/6 stories done; refusal eval needs API keys on staging | 2026-09-23
H1 | EPIC-H | Story | As an employee, I can ask a question in plain language and get an answer from our own documents. | p95 first token under 2 seconds. |  | EPIC-H | High | 13 |  |  | M3 Retrieval layer | p1,m3 | Done | 4/4 sub-tasks done | 2026-09-23
H1-T1 | H1 | Sub-task | Retrieval to context assembly |  |  |  | High |  | 10 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done |  | 2026-09-22
H1-T2 | H1 | Sub-task | Answer generation prompt requiring citations |  |  |  | High |  | 12 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | [answer] prompt | 2026-09-22
H1-T3 | H1 | Sub-task | SSE streaming endpoint |  |  |  | High |  | 8 | Backend | M3 Retrieval layer | backend | Done | retrieval → token* → done | 2026-09-22
H1-T4 | H1 | Sub-task | Ask screen with streaming render (S15) |  |  |  | High |  | 14 | Frontend | M3 Retrieval layer | frontend | Done | S15 | 2026-09-22
H2 | EPIC-H | Story | As an employee, every answer cites the source SOP, version and step, and links to it. | An answer with zero citations is a bug, not a valid response. |  | EPIC-H | High | 8 |  |  | M3 Retrieval layer | p1,m3 | Done | 3/3 sub-tasks done | 2026-09-23
H2-T1 | H2 | Sub-task | Citation resolution to document, version and step |  |  |  | High |  | 8 | Backend | M3 Retrieval layer | backend | Done |  | 2026-09-22
H2-T2 | H2 | Sub-task | Citation chips with deep link to step |  |  |  | High |  | 10 | Frontend | M3 Retrieval layer | frontend | Done | deep link to step/section/block | 2026-09-22
H2-T3 | H2 | Sub-task | Block answers that carry no citation |  |  |  | High |  | 4 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | zero-citation → refusal | 2026-09-22
H3 | EPIC-H | Story | As an employee, when no approved document covers my question, the bot says so instead of guessing. | Refusal is a designed state with actions attached, not a fallback. |  | EPIC-H | High | 8 |  |  | M3 Retrieval layer | p1,m3 | In Progress | 2/3 sub-tasks done | 2026-09-23
H3-T1 | H3 | Sub-task | Confidence threshold and refusal path |  |  |  | High |  | 8 | AI/Pipeline | M3 Retrieval layer | ai-pipeline | Done | min_score | 2026-09-22
H3-T2 | H3 | Sub-task | Refusal UI with record and request actions |  |  |  | High |  | 8 | Design | M3 Retrieval layer | design | Done | Record it / Request | 2026-09-22
H3-T3 | H3 | Sub-task | Refusal eval: 15 deliberately unanswerable questions |  |  |  | High |  | 8 | QA | M3 Retrieval layer | qa | Blocked | ready: demo corpus + 20/15 set (spike/retrieval-eval/demo), retrieval:seed-corpus, retrieval:eval --answer; needs OPENAI_API_KEY + ANTHROPIC_API_KEY on staging to run against the real models | 2026-09-23
H4 | EPIC-H | Story | As an employee, I can ask follow-up questions in the same conversation. |  |  | EPIC-H | High | 5 |  |  | M3 Retrieval layer | p1,m3 | Done | 2/2 sub-tasks done | 2026-09-23
H4-T1 | H4 | Sub-task | Session history and context window management |  |  |  | High |  | 8 | Backend | M3 Retrieval layer | backend | Done | Conversation::history — 6 turns / 6,000 chars / 1,500 per turn, access-checked; standalone query for retrieval | 2026-09-23
H4-T2 | H4 | Sub-task | Multi-turn context retention tests |  |  |  | High |  | 4 | QA | M3 Retrieval layer | qa | Done | ChatConversationTest: follow-up rewrite ([condense]), bounded history, no replay after access loss, scoped sessions, privacy, turn order | 2026-09-23
H5 | EPIC-H | Story | As an employee, I can rate an answer helpful or not. |  |  | EPIC-H | High | 3 |  |  | M3 Retrieval layer | p1,m3 | Done | 2/2 sub-tasks done | 2026-09-23
H5-T1 | H5 | Sub-task | Rating endpoint and storage on chat_messages |  |  |  | High |  | 3 | Backend | M3 Retrieval layer | backend | Done |  | 2026-09-22
H5-T2 | H5 | Sub-task | Rating control in answer UI |  |  |  | High |  | 3 | Frontend | M3 Retrieval layer | frontend | Done |  | 2026-09-22
H6 | EPIC-H | Story | As an admin, I can see which questions were refused, so I know which SOP to record next. | Turns the chatbot's failures into the customer's content roadmap. |  | EPIC-H | High | 5 |  |  | M3 Retrieval layer | p1,m3 | Done | 2/2 sub-tasks done | 2026-09-23
H6-T1 | H6 | Sub-task | Refused query aggregation and ranking |  |  |  | High |  | 6 | Backend | M3 Retrieval layer | backend | Done | grouped by meaning (FR-614): embeddings, cosine ≥ 0.8, labelled by most-asked phrasing with variants | 2026-09-23
H6-T2 | H6 | Sub-task | Knowledge gaps screen with Record-this action (S20) |  |  |  | High |  | 10 | Frontend | M3 Retrieval layer | frontend | Done | S20 | 2026-09-22
EPIC-I |  | Epic | I — AI utilities | Rewrite, translation and instant answers. | AI utilities | [6 empty] | epic | Done | 10/10 sub-tasks done, 4/4 stories done | 2026-09-23
I1 | EPIC-I | Story | As an editor, I can have AI rewrite rough notes into clear procedure language, shown as a proposal I accept or reject. | Never applied silently. The server never mutates a document from an AI call. |  | EPIC-I | High | 8 |  |  | M4 Open paid tiers | p1,m4 | Done | 3/3 sub-tasks done | 2026-09-23
I1-T1 | I1 | Sub-task | Rewrite endpoint returning a proposal |  |  |  | High |  | 8 | AI/Pipeline | M4 Open paid tiers | ai-pipeline | Done | POST /ai/rewrite; f826ebd | 2026-09-22
I1-T2 | I1 | Sub-task | Side-by-side accept and reject panel |  |  |  | High |  | 12 | Frontend | M4 Open paid tiers | frontend | Done | assist panel | 2026-09-22
I1-T3 | I1 | Sub-task | Never-auto-apply guard and regression test |  |  |  | High |  | 4 | QA | M4 Open paid tiers | qa | Done | AssistanceTest | 2026-09-22
I2 | EPIC-I | Story | As an editor, I can translate a document with one click into a linked translation. | Creates a linked translation rather than replacing the source. |  | EPIC-I | High | 8 |  |  | M4 Open paid tiers | p1,m4 | Done | 3/3 sub-tasks done | 2026-09-23
I2-T1 | I2 | Sub-task | Translation endpoint creating a linked document |  |  |  | High |  | 8 | AI/Pipeline | M4 Open paid tiers | ai-pipeline | Done | POST /ai/translate | 2026-09-22
I2-T2 | I2 | Sub-task | Translation UI and language picker |  |  |  | High |  | 8 | Frontend | M4 Open paid tiers | frontend | Done |  | 2026-09-22
I2-T3 | I2 | Sub-task | Bidirectional translation link model |  |  |  | High |  | 5 | Database | M4 Open paid tiers | database | Done | Document::source()/translations(); GET /documents/{id} and /published return source + translations (visible, published-only for readers); reader/editor links; assist panel blocks duplicate languages | 2026-09-23
I3 | EPIC-I | Story | As an editor, a translation is flagged stale when its source is re-approved. |  |  | EPIC-I | Medium | 5 |  |  | M4 Open paid tiers | p2,m4 | Done | 2/2 sub-tasks done | 2026-09-23
I3-T1 | I3 | Sub-task | Stale trigger on source re-approval |  |  |  | Medium |  | 4 | Database | M4 Open paid tiers | database | Done | Workflow::approve sets translation_stale | 2026-09-22
I3-T2 | I3 | Sub-task | Stale indicator in reader and document list |  |  |  | Medium |  | 5 | Frontend | M4 Open paid tiers | frontend | Done | reader banner + source link, editor banner + source link, space browser shows language tag and "out of date" | 2026-09-23
I4 | EPIC-I | Story | As a user, search shows a direct instant answer above the result list. | Styled as a document extract, not a chat bubble. |  | EPIC-I | Medium | 5 |  |  | M4 Open paid tiers | p2,m4 | Done | 2/2 sub-tasks done | 2026-09-23
I4-T1 | I4 | Sub-task | Instant answer generation from top result |  |  |  | Medium |  | 6 | AI/Pipeline | M4 Open paid tiers | ai-pipeline | Done |  | 2026-09-22
I4-T2 | I4 | Sub-task | Instant answer block in search (S14) |  |  |  | Medium |  | 7 | Frontend | M4 Open paid tiers | frontend | Done |  | 2026-09-22
EPIC-J |  | Epic | J — Handbook & acknowledgements | Policy distribution and proof that people read it. | Handbook & acknowledgements | [6 empty] | epic | Done | 10/10 sub-tasks done, 5/5 stories done | 2026-09-22
J1 | EPIC-J | Story | As an HR manager, I can designate a space as the employee handbook with an ordered reader view. |  |  | EPIC-J | High | 5 |  |  | M4 Open paid tiers | p1,m4 | Done | 2/2 sub-tasks done | 2026-09-22
J1-T1 | J1 | Sub-task | is_handbook flag and ordered view API |  |  |  | High |  | 5 | Backend | M4 Open paid tiers | backend | Done | GET /handbook, PUT /handbook/order | 2026-09-22
J1-T2 | J1 | Sub-task | Handbook reader with contents rail (S16) |  |  |  | High |  | 10 | Frontend | M4 Open paid tiers | frontend | Done | S16; 57d4bd7 | 2026-09-22
J2 | EPIC-J | Story | As an HR manager, I can require acknowledgement of a policy from assigned employees. | Acknowledgement binds to a version, not a document. |  | EPIC-J | High | 8 |  |  | M4 Open paid tiers | p1,m4 | Done | 3/3 sub-tasks done | 2026-09-22
J2-T1 | J2 | Sub-task | acknowledgements schema, unique per version and user |  |  |  | High |  | 5 | Database | M4 Open paid tiers | database | Done |  | 2026-09-22
J2-T2 | J2 | Sub-task | Assign acknowledgement targets API |  |  |  | High |  | 6 | Backend | M4 Open paid tiers | backend | Done |  | 2026-09-22
J2-T3 | J2 | Sub-task | Acknowledgement tracking screen, both views (S17) |  |  |  | High |  | 12 | Frontend | M4 Open paid tiers | frontend | Done | S17 | 2026-09-22
J3 | EPIC-J | Story | As an employee, I can acknowledge a policy and it records the version and timestamp. |  |  | EPIC-J | High | 3 |  |  | M4 Open paid tiers | p1,m4 | Done | 2/2 sub-tasks done | 2026-09-22
J3-T1 | J3 | Sub-task | Acknowledge endpoint |  |  |  | High |  | 3 | Backend | M4 Open paid tiers | backend | Done |  | 2026-09-22
J3-T2 | J3 | Sub-task | Sticky acknowledgement bar and confirmation |  |  |  | High |  | 5 | Frontend | M4 Open paid tiers | frontend | Done |  | 2026-09-22
J4 | EPIC-J | Story | As an HR manager, publishing a new version re-triggers acknowledgement. |  |  | EPIC-J | Medium | 3 |  |  | M4 Open paid tiers | p2,m4 | Done | 2/2 sub-tasks done | 2026-09-22
J4-T1 | J4 | Sub-task | Supersede trigger on new approved version |  |  |  | Medium |  | 4 | Database | M4 Open paid tiers | database | Done | ack per version + AcknowledgementDueNotification | 2026-09-22
J4-T2 | J4 | Sub-task | Re-trigger behaviour tests |  |  |  | Medium |  | 3 | QA | M4 Open paid tiers | qa | Done | AcknowledgementTest | 2026-09-22
J5 | EPIC-J | Story | As an HR manager, I can export the acknowledgement record to CSV. | One row per user per document version with timestamp. |  | EPIC-J | Medium | 2 |  |  | M4 Open paid tiers | p2,m4 | Done | 1/1 sub-tasks done | 2026-09-22
J5-T1 | J5 | Sub-task | CSV export endpoint |  |  |  | Medium |  | 5 | Backend | M4 Open paid tiers | backend | Done |  | 2026-09-22
EPIC-K |  | Epic | K — Billing & plans | Free, Pro and Team tiers with honest limit enforcement. | Billing & plans | [6 empty] | epic | In Progress | 10/11 sub-tasks done, 3/4 stories done; only the payment-provider driver remains, blocked on the provider decision | 2026-09-23
K1 | EPIC-K | Story | As a workspace, I start on Free with 3 users and 50 documents. | Free is capped on documents, not features, so AI value is visible before the paywall. |  | EPIC-K | High | 5 |  |  | M4 Open paid tiers | p1,m4 | Done | 3/3 sub-tasks done | 2026-09-23
K1-T1 | K1 | Sub-task | subscriptions and usage_counters schema |  |  |  | High |  | 5 | Database | M4 Open paid tiers | database | Done | subscriptions table created (migration 001600, doc 04 v2.9); usage_counters superseded by live counters (Billing\Usage) | 2026-09-23
K1-T2 | K1 | Sub-task | Default plan assignment on workspace creation |  |  |  | High |  | 3 | Backend | M4 Open paid tiers | backend | Done |  | 2026-09-22
K1-T3 | K1 | Sub-task | Usage counting hooks across billable actions |  |  |  | High |  | 6 | Backend | M4 Open paid tiers | backend | Done |  | 2026-09-22
K2 | EPIC-K | Story | As an admin, I can upgrade to Pro or Team and manage billing. |  |  | EPIC-K | High | 8 |  |  | M4 Open paid tiers | p1,m4 | In Progress | 2/3 sub-tasks done | 2026-09-23
K2-T1 | K2 | Sub-task | Payment provider integration and webhooks |  |  |  | High |  | 14 | Backend | M4 Open paid tiers | backend | Blocked | provider-independent part done: BillingProvider driver interface, subscriptions table, POST /billing/webhook (normalised events), Null + Fake drivers, app.yaml settings. The real driver is one class once the provider is chosen (open decision 03 §12) | 2026-09-23
K2-T2 | K2 | Sub-task | Plan change, seat handling and proration |  |  |  | High |  | 8 | Backend | M4 Open paid tiers | backend | Done | Plans: upgrade/more seats at once (provider prorates), downgrade/fewer seats scheduled at period end (billing:apply-scheduled hourly + webhook), refused with counts when over the new limits, Team >10 seats refused (open decision); S22 plan chooser + seats + scheduled notice; PlanChangeTest | 2026-09-23
K2-T3 | K2 | Sub-task | Billing and usage screen (S22) |  |  |  | High |  | 10 | Frontend | M4 Open paid tiers | frontend | Done | S22; 4c59e48 | 2026-09-22
K3 | EPIC-K | Story | As a system, plan limits are enforced with a clear message, not a silent failure. | 429 with plan_limit_exceeded and the counter in details. |  | EPIC-K | High | 5 |  |  | M4 Open paid tiers | p1,m4 | Done | 3/3 sub-tasks done | 2026-09-23
K3-T1 | K3 | Sub-task | Limit enforcement returning 429 across endpoints |  |  |  | High |  | 8 | Backend | M4 Open paid tiers | backend | Done | 429 plan_limit_exceeded / 402 plan_required | 2026-09-22
K3-T2 | K3 | Sub-task | Approaching-limit notice in the app shell |  |  |  | High |  | 5 | Frontend | M4 Open paid tiers | frontend | Done | shell limit notice | 2026-09-22
K3-T3 | K3 | Sub-task | Per-tier limit enforcement tests |  |  |  | High |  | 5 | QA | M4 Open paid tiers | qa | Done | UsageTest | 2026-09-22
K4 | EPIC-K | Story | As an admin, I can see usage against my plan limits. |  |  | EPIC-K | High | 3 |  |  | M4 Open paid tiers | p1,m4 | Done | 2/2 sub-tasks done | 2026-09-23
K4-T1 | K4 | Sub-task | Usage endpoint returning counters against caps |  |  |  | High |  | 3 | Backend | M4 Open paid tiers | backend | Done | GET /usage | 2026-09-22
K4-T2 | K4 | Sub-task | Usage-against-caps display |  |  |  | High |  | 5 | Frontend | M4 Open paid tiers | frontend | Done |  | 2026-09-22
EPIC-L |  | Epic | L — Analytics & operations | Admin insight, review cadence and pipeline health. | Analytics & operations | [6 empty] | epic | Done | 8/8 sub-tasks done, 4/4 stories done | 2026-09-23
L1 | EPIC-L | Story | As an admin, I see documents by state, approval throughput and chat volume. |  |  | EPIC-L | Medium | 5 |  |  | M5 Scale | p2,m5 | Done | 2/2 sub-tasks done | 2026-09-23
L1-T1 | L1 | Sub-task | Analytics aggregation queries |  |  |  | Medium |  | 8 | Backend | M5 Scale | backend | Done | AnalyticsController::overview | 2026-09-22
L1-T2 | L1 | Sub-task | Analytics section of insights screen (S20) |  |  |  | Medium |  | 8 | Frontend | M5 Scale | frontend | Done |  | 2026-09-22
L2 | EPIC-L | Story | As an admin, I can see stale documents past their review date. |  |  | EPIC-L | Medium | 5 |  |  | M5 Scale | p2,m5 | Done | 2/2 sub-tasks done | 2026-09-23
L2-T1 | L2 | Sub-task | review_due_at and workspace review cadence setting |  |  |  | Medium |  | 4 | Backend | M5 Scale | backend | Done | review cadence setting + review_due_at on approval | 2026-09-22
L2-T2 | L2 | Sub-task | Past-review list and owner dashboard |  |  |  | Medium |  | 8 | Frontend | M5 Scale | frontend | Done | GET /analytics/past-review + list on Insights; GET /me/documents owner dashboard (/my-documents) with needs ranked most urgent first | 2026-09-23
L3 | EPIC-L | Story | As an operator, I'm alerted when an approved document has no current index entry. | Correctness invariant: approved implies indexed. |  | EPIC-L | Medium | 5 |  |  | M5 Scale | p2,m5 | Done | 2/2 sub-tasks done | 2026-09-23
L3-T1 | L3 | Sub-task | Monitor job comparing approved documents to chunks |  |  |  | Medium |  | 6 | Infra | M5 Scale | infra | Done | retrieval:check-index every 10 min (built under G1-T5): re-queue, stray-chunk cleanup, admin notice | 2026-09-23
L3-T2 | L3 | Sub-task | Alert routing and runbook |  |  |  | Medium |  | 5 | Infra | M5 Scale | infra | Done | `alerts` log channel (stderr + Slack at warning when LOG_SLACK_WEBHOOK_URL set); app.yaml platform alerts; infra/runbooks (index, billing, pipeline) | 2026-09-23
L4 | EPIC-L | Story | As an operator, I can see cost per generated SOP by workspace. | Margin signal. Watch during design-partner phase before pricing decisions. |  | EPIC-L | Medium | 3 |  |  | M5 Scale | p2,m5 | Done | 2/2 sub-tasks done | 2026-09-23
L4-T1 | L4 | Sub-task | LLM cost logging per workspace and job |  |  |  | Medium |  | 5 | Backend | M5 Scale | backend | Done | cost_usd on pipeline_jobs and audit metadata | 2026-09-22
L4-T2 | L4 | Sub-task | Internal cost-per-SOP view |  |  |  | Medium |  | 4 | Backend | M5 Scale | backend | Done | ops:cost-report [--month] [--csv]: per workspace pipeline $, $/SOP, chat $, assist $, plan price, margin %; chat_messages.cost_usd added | 2026-09-23
EPIC-M |  | Epic | M — Platform & delivery | Design system, Aura theming, environments, CI/CD and observability. Prerequisites, not overhead. | Platform & delivery | [6 empty] | epic | In Progress | 9/17 sub-tasks done, 1/5 stories done | 2026-09-22
M1 | EPIC-M | Story | As a developer, I have design tokens and a component library so screens are consistent and fast to build. | Smaller than v1.0 assumed: PrimeNG supplies the generic controls. Document surfaces stay custom. |  | EPIC-M | Highest | 5 |  |  | M0 Foundation | p0,m0 | Done | 3/3 sub-tasks done | 2026-09-22
M1-T1 | M1 | Sub-task | Token system: colour, type, spacing from screen spec |  |  |  | Highest |  | 8 | Design | M0 Foundation | design | Done | styles.scss tokens | 2026-09-22
M1-T2 | M1 | Sub-task | Custom document surfaces: reader, step list, control block, diff view |  |  |  | Highest |  | 14 | Frontend | M0 Foundation | frontend | Done |  | 2026-09-22
M1-T3 | M1 | Sub-task | State pill component, word always present alongside colour |  |  |  | Highest |  | 4 | Frontend | M0 Foundation | frontend | Done |  | 2026-09-22
M2 | EPIC-M | Story | As a developer, CI runs lint, type-check, tests and build on every push. |  |  | EPIC-M | Highest | 5 |  |  | M0 Foundation | p0,m0 | In Progress | 1/2 sub-tasks done | 2026-09-22
M2-T1 | M2 | Sub-task | CI: Pint, PHPStan, PHPUnit, ESLint, Angular build |  |  |  | Highest |  | 8 | Infra | M0 Foundation | infra | Done | ci.yml | 2026-09-22
M2-T2 | M2 | Sub-task | CD to staging on merge, production behind a manual gate |  |  |  | Highest |  | 8 | Infra | M0 Foundation | infra | To Do | CD not configured | 2026-09-22
M3 | EPIC-M | Story | As a developer, environments are separated and schema changes ship as versioned migrations. | No manual production SQL, ever. |  | EPIC-M | Highest | 5 |  |  | M0 Foundation | p0,m0 | In Progress | 2/4 sub-tasks done | 2026-09-22
M3-T1 | M3 | Sub-task | App Platform spec in infra/do/app.yaml: web plus worker components |  |  |  | Highest |  | 10 | Infra | M0 Foundation | infra | Done | + scheduler component | 2026-09-22
M3-T2 | M3 | Sub-task | Managed MySQL and Valkey per environment with TLS enforced |  |  |  | Highest |  | 6 | Infra | M0 Foundation | infra | In Progress | spec written; provisioning is an ops step | 2026-09-22
M3-T3 | M3 | Sub-task | Laravel migrations as a pre-deploy job, with rollback drill |  |  |  | Highest |  | 6 | Infra | M0 Foundation | infra | In Progress | pre-deploy migrate job; rollback drill not done | 2026-09-22
M3-T4 | M3 | Sub-task | FFmpeg in the worker image for frame extraction |  |  |  | Highest |  | 3 | Infra | M0 Foundation | infra | Done | Dockerfile.worker | 2026-09-22
M4 | EPIC-M | Story | As an operator, I can see pipeline health and get alerted before users notice. |  |  | EPIC-M | High | 5 |  |  | M1 Prove the wedge | p1,m1 | In Progress | 0/4 sub-tasks done | 2026-09-22
M4-T1 | M4 | Sub-task | Sentry SDK wired into Laravel and Angular with release tagging |  |  |  | High |  | 5 | Infra | M1 Prove the wedge | infra | To Do |  | 2026-09-22
M4-T2 | M4 | Sub-task | Structured logging per pipeline stage to stdout |  |  |  | High |  | 5 | Infra | M1 Prove the wedge | infra | In Progress | pipeline_jobs status/errors; structured stdout logging not added | 2026-09-22
M4-T3 | M4 | Sub-task | Metrics and dashboards: success rate, latency, cost per SOP |  |  |  | High |  | 8 | Infra | M1 Prove the wedge | infra | To Do |  | 2026-09-22
M4-T4 | M4 | Sub-task | Alerts: generation failures, embedding backlog, unindexed approved docs |  |  |  | High |  | 5 | Infra | M1 Prove the wedge | infra | To Do |  | 2026-09-22
M5 | EPIC-M | Story | As a developer, the PrimeNG Aura preset is configured to the Hub brand without colliding with document state. | Gold and draft amber share a hue family, and Aura paints primary across every control. Left at default this breaks the rule that colour means state. |  | EPIC-M | Highest | 8 |  |  | M0 Foundation | p0,m0 | In Progress | 3/4 sub-tasks done | 2026-09-22
M5-T1 | M5 | Sub-task | Override Aura primary palette to navy #1E2761 |  |  |  | Highest |  | 6 | Frontend | M0 Foundation | frontend | Done |  | 2026-09-22
M5-T2 | M5 | Sub-task | Map ice #CADCFC to selection and focus; confine gold to brand surfaces |  |  |  | Highest |  | 5 | Design | M0 Foundation | design | Done |  | 2026-09-22
M5-T3 | M5 | Sub-task | Override Aura radius and density toward the controlled-document look |  |  |  | Highest |  | 6 | Frontend | M0 Foundation | frontend | Done |  | 2026-09-22
M5-T4 | M5 | Sub-task | Verify review-blue pill against navy chrome and check AA contrast |  |  |  | Highest |  | 4 | QA | M0 Foundation | qa | In Progress | visual check pending | 2026-09-22

## Progress
Progress as of 2026-09-23 — derived from the Status column on 'Jira Import'
Epic | Name | Sub-tasks | Done | In Progress | To Do | Blocked | % done | Stories done
A | A — Foundation & tenancy | 20 | 20 | 0 | 0 | 0 | 100% | 5/5
B | B — Editor & document model | 21 | 21 | 0 | 0 | 0 | 100% | 7/7
C | C — Recording capture | 13 | 13 | 0 | 0 | 0 | 100% | 4/4
D | D — AI SOP generation | 22 | 17 | 0 | 0 | 5 | 77% | 3/6
E | E — Governance | 18 | 18 | 0 | 0 | 0 | 100% | 6/6
F | F — Permissions | 9 | 9 | 0 | 0 | 0 | 100% | 3/3
G | G — Search & retrieval | 19 | 16 | 0 | 0 | 3 | 84% | 3/6
H | H — Chatbot | 16 | 15 | 0 | 0 | 1 | 94% | 5/6
I | I — AI utilities | 10 | 10 | 0 | 0 | 0 | 100% | 4/4
J | J — Handbook & acknowledgements | 10 | 10 | 0 | 0 | 0 | 100% | 5/5
K | K — Billing & plans | 11 | 10 | 0 | 0 | 1 | 91% | 3/4
L | L — Analytics & operations | 8 | 8 | 0 | 0 | 0 | 100% | 4/4
M | M — Platform & delivery | 17 | 9 | 4 | 4 | 0 | 53% | 1/5
Total |  | 194 | 176 | 4 | 4 | 10 | 91%
Status meaning
Done | built, lint-clean, unit/feature tests written. As of 2026-09-23 the API passes the raw-query check, Pint, PHPStan level 6 and all 113 PHPUnit tests on SQLite and on MySQL 8.4 locally; the web app passes lint, 35 tests and the production build; CI confirmation pending the push
In Progress | partly built — see the Status note for what is missing
To Do | not started
Blocked | waiting on a decision, keys or material from the team (transcription provider, billing provider, real recordings)
Commits: docs 5029b6e/3bb6c31 · spike 55515b8 · M0 b58a0df · A 11876e5/1c63003 · B 8f9ead3 · skeleton b0f807f · C b92964a · D 34a494e · CI 5e61028 · E 7d65832 · F 754a141 · M3 a7cf59b · docs 39e31cd · I 57d4bd7 · J b107f9e · K 4c59e48 · L 3fb9d6c · B1 44e896b · Pint 5484896 · FR-8xx f826ebd

## Epic Summary
Epic | Name | Stories | Tasks | Story Points | Estimate (h) | Estimate (days) | % of total
A | Foundation & tenancy | 5 | 20
B | Editor & document model | 7 | 21
C | Recording capture | 4 | 13
D | AI SOP generation | 6 | 22
E | Governance | 6 | 18
F | Permissions | 3 | 9
G | Search & retrieval | 6 | 19
H | Chatbot | 6 | 16
I | AI utilities | 4 | 10
J | Handbook & acknowledgements | 5 | 10
K | Billing & plans | 4 | 11
L | Analytics & operations | 4 | 8
M | Platform & delivery | 5 | 17
Total
| Assumption — hours per working day | 6
| Assumption — team capacity, developer-days per week | 10
Estimates are engineering hours only. They exclude discovery, design partner support, recruitment and holiday.

## Milestone Plan
Milestone | Focus | Stories | Story Points | Estimate (h) | Estimate (days) | Elapsed weeks at capacity
M0 Foundation | Auth, tenancy, editor, design system, CI | 16
M1 Prove the wedge | Recording capture and AI SOP generation | 11
M2 Design partners | Governance and permissions, 5 partners onboarded | 9
M3 Retrieval layer | Search, chunking, chatbot with citations | 12
M4 Open paid tiers | AI utilities, handbook, billing | 13
M5 Scale | Analytics, review cadence, pipeline health | 4
Total
Elapsed weeks assumes the capacity on Epic Summary and no parallelism between milestones. M2 and M3 overlap in the roadmap, so real elapsed time is shorter than this total.

## Component Load
Component | Tasks | Estimate (h) | % of build
AI/Pipeline
Backend
Database
Design
Frontend
Full stack
Infra
QA
Total

## Import Guide
How to import this into Jira
1 | Save the 'Jira Import' sheet as CSV (File > Save As > CSV, that sheet only).
2 | In Jira: Settings > System > External System Import > CSV.
3 | Upload the CSV. On the field-mapping screen, map the columns as below.
4 | Tick 'Map field value' for Priority if your scheme uses different names.
5 | Import epics and stories first if your Jira rejects sub-tasks in one pass — filter Issue Type, import in two runs, then re-run with sub-tasks.
Column | Maps to
Issue ID | Issue ID (used only to link parents during import)
Parent ID | Parent ID
Issue Type | Issue Type
Summary | Summary
Description | Description
Epic Name | Epic Name (epics only)
Epic Link | Epic Link (stories only)
Priority | Priority
Story Points | Story Points (custom field)
Original Estimate (h) | Original Estimate — append 'h' or set the unit to hours
Component | Component/s — create these in the project first
Milestone | Sprint, Fix Version, or a custom field, whichever you use
Labels | Labels
Estimating basis
Story points | Carried from the product backlog document. They size relative complexity and are not converted from hours.
Task hours | Estimated per task, independently of points. Story hours are the sum of their sub-tasks, so points and hours are two separate views and will not correlate perfectly — that is intentional.
Excluded | Discovery, design-partner recruitment and support, project management, holiday, onboarding and rework after user feedback.
Confidence | Epics A, B, C, E, F, J, K and M are conventional work and estimate reliably. Epic D (generation) and Epic G/H (retrieval) contain genuine research risk — treat those hours as a first pass to be revised after the first ten real recordings.
Known correction
Epic B total | The product backlog document listed Epic B as 34 points. The stories in it actually sum to 40, and the backlog total is 367 rather than 361. This workbook uses the corrected figures and the backlog document has been updated to match.
Epic M is new | Design system, CI/CD, environments and observability were not in the original backlog. They are prerequisites rather than overhead, so they are estimated here.