FLOWZAPP

Roadmap & Milestones

M0 to M5 with entry, exit and go/no-go gates

Version 1.0  ·  Project documentation  ·  2026

The deck names four moves: prove the wedge, recruit design partners, ship the retrieval layer, open the paid tiers. This document turns those into milestones with entry criteria, scope and exit criteria.

Durations assume a small team (2–3 engineers plus the project lead). Adjust the calendar, not the sequence — the sequence is the strategy.

## M0 — Foundation

~3 weeks · Epics A, B (partial)

Everything that has to exist before the wedge can be built.

- Auth, workspace creation, invites, roles

- Spaces, folders, document CRUD

- Rich text editor with core block types and autosave

- Application-layer workspace scoping on every tenant model, with the schema conformance test and cross-tenant suite in CI

Exit criteria

- A user can sign up, invite a colleague, create a folder and write a document.

- The cross-tenant test suite passes: no query from workspace B can read workspace A.

## M1 — Prove the wedge

~5 weeks · Epics C, D

Ship recording → AI-drafted SOP end to end. That single flow is the demo and the wedge.

- Browser screen + voice capture, resumable upload

- Transcription with timestamps

- Action segmentation and key-frame extraction

- Structured SOP generation into the editor

- Per-step link back to the source timestamp

- Processing status visible at every stage

Exit criteria — all must hold on ten real recordings, not synthetic ones

- A 15-minute recording produces a usable draft in under 5 minutes (p90).

- A reviewer can approve the draft after light editing, not a rewrite. Track median edit distance and set the bar before you start, so the result is measured rather than argued.

- The flow demos in under 4 minutes without narration covering for gaps.

This is the only milestone that can fail the whole product. If drafts are consistently rewritten from scratch, stop and fix generation before building anything else. Do not proceed to M2 on a "good enough for now" draft — every later milestone assumes generation works.

## M2 — Design partners

~4 weeks, overlapping M3 · Recruit 5

Recruit 5 agencies or ops teams to run real processes through it for free, in exchange for feedback.

- Recruit from the beachhead: agencies and ops teams of 10–200

- Onboard each with a live recording session — watch them record, do not just send a link

- Instrument abandonment: where in the flow do people stop?

- Weekly feedback cadence; one shared changelog

Exit criteria

- 5 workspaces with ≥ 10 approved documents each

- ≥ 60% of uploaded recordings reach an approved SOP

- Three named quotes usable in launch material

Parallel engineering during M2: Epics E (governance) and F (permissions). Design partners will hit approval and permission gaps immediately; these are cheap to build and expensive to retrofit.

## M3 — Ship the retrieval layer

~5 weeks · Epics G, H

Chatbot with citations over approved content only — the feature that converts Free to Team.

- Chunking by step and section; embedding on approval

- Hybrid semantic + keyword search with in-query permission filtering

- Chatbot with citations, deep links, multi-turn, and explicit refusal

- Answer rating and the knowledge-gaps report

Exit criteria

- Zero answers sourced from drafts or archived content, verified by test.

- Every non-refused answer carries at least one citation.

- Permission test: user removed from a space gets zero results from it, immediately.

- p95 chat first-token under 2 s.

## M4 — Open the paid tiers

~4 weeks · Epics I, J, K

Launch Pro and Team once approval workflow and permissions are stable.

- AI rewrite and translation

- Employee handbook and acknowledgements

- Free / Pro / Team plans, limits, billing, usage display

- Onboarding: empty-state that pushes straight to the first recording

Exit criteria

- Plan limits enforced with clear messaging, verified for each tier.

- Billing lifecycle tested: upgrade, downgrade, seat change, failed payment.

- At least 2 design partners convert to paid.

## M5 — Scale & analytics

Ongoing · Epic L and beyond

- Admin analytics, stale-document review cadence, cost-per-SOP monitoring

- Integrations (Slack query surface first — the answer should reach people where they ask)

- Vector store and embeddings provider revisited at scale

- Transactional email provider replacing Gmail SMTP, which caps near 2,000 recipients a day

- Enterprise groundwork: SSO/SAML, SOC 2, data residency

## Sequence at a glance

Weeks   1   3   5   7   9  11  13  15  17  19  21

M0    ████

M1        ██████████

M2                  ████████

M3                  ██████████

M4                            ████████

M5                                    ████████→

M2 and M3 overlap deliberately: design partners generate the real retrieval queries that make M3 correct, and M3 gives them the reason to stay.

## Milestone gates

Each gate is a go/no-go, not a status update:

| Gate | Question | If no |
| --- | --- | --- |
| M0 → M1 | Is tenancy isolation provably correct? | Fix before touching AI. A leak later is unrecoverable. With no RLS, "provably" means the conformance test and cross-tenant suite both pass. |
| M1 → M2 | Do generated drafts get approved with light edits? | Iterate generation. Do not recruit partners for a broken demo. |
| M2 → M3 | Are partners producing approved documents on their own? | The problem is product, not retrieval. Fix adoption first. |
| M3 → M4 | Does the chatbot refuse correctly and cite always? | Do not sell it. One confident wrong answer costs the account. |
| M4 → M5 | Did design partners convert? | Revisit packaging before scaling spend. |

## What deliberately waits

Named here so they don't get argued back in mid-sprint: native desktop/mobile capture, real-time collaborative editing, public help centres, deep third-party integrations, white-labelling, self-hosting, SSO/SOC 2/HIPAA.

Healthcare and manufacturing are high-value but slow to buy. Land agencies, ops and IT first; the compliance work follows the revenue, not the other way around.